Action Plan

of

Environmental Education and

Public

Awareness

2004 - 2006

Ministry of  the Environment of the Czech Republic

Preface

In the autumn of 2000, the Government of the Czech Republic approved Resolution 1048/2000 on the State Program of Environmental Education and Public Awareness (SP EEA) in the Czech Republic as a strategic document providing for the development of EEA in the long-term future. Simultaneously, the Action Plan for SP EEA was adopted for 2001 - 2003.

SP EEA and its Action Plan for 2001 - 2003 were adopted in connection with the accession of CR to the European Union and as part of implementation of Directive 90/313/EEC on free access to information on the environment (on January 28, 2003, this was replaced by Directive 2003/4/EC on public access to information on the environment and cancelling Directive 90/313/EEC). Fulfilling of the Action Plan has been evaluated each year as a separate part of the Report on the Environment.

The first 3 years of implementation of SPEEA can be evaluated favourably; a great many events have occurred, that have contributed to EEA and thus to extending the consciousness of environmental issues amongst the general public. A good example is the preparation and approval of the regional EEA conceptions and systems, introducing obligatory environmental knowledge in the framework of further education of pedagogical workers and employees of the public administration, inclusion of a separate chapter on support for EEA from SEF CR (specifically, this consists in individual programs 8.1 and 8.2 of Annex I of the ME Directive on provision of funds from SEF CR), incorporation of environmental viewpoints and EEA into laws and subordinate legislation and conceptual materials (in 2002, the Government of CR included EEA in its program declarations), development of Local Agendas 21, etc.

The important instruments assisting in fulfilling the tasks of the Action Plan for 2001-2003 include the program of the National Network of Environmental Education and Public Awareness Centres (a specialized public contract is announced each year at ME). The International Working Group for EEA at ME was an important consulting body in this period and the Intersectoral Agreement on cooperation in the Area of Environmental Education and Public Awareness between the Ministry of the Environment and the Ministry of Education, Youth and Sports (updated in 2004) also played an important role.

The updated Action Plan for 2004 - 2006 is a response to instigations following from the results of evaluation of implementation of the previous Action Plan for 2001 - 2003. Briefly, compared to the past, the program is oriented more towards sustainable development, greater emphasis is placed on consulting and enlightenment and work with the public (e.g. increased support for Local Agendas 21), which has a greater effect on the possibilities in requesting financial means from EU structural funds and enables provision for greater scope and compatibility of EEA with development of society and its needs in general. The Action Plan for 2004 - 2006 is targeted towards target groups i) employees in administrative authorities, officials in territorial planning units and elected members of municipal councils; ii) children, youth, pedagogical and professional workers; iii) the business and tertiary sphere and iv) is also concerned with provision of information, enlightenment and consulting for the general public.

Similar to the prepared updating of the State Environmental Policy, the Action Plan for 2004 - 2006 is based on the following sources and documents and international agreements:

- the 6th  Environmental Action Program of the European Communities (6th EAP), adopted in Brussels on January 24, 2001;

- the OECD Environmental Strategy for the first decade of the 21st century ENV/EPOC(2001)13/REV4, adopted in Paris on May 16, 2001 (the Strategy states that support for EEA creates a basis for identification, adoption and successful implementation of environmental policies);

- the European Union Strategy for sustainable development, adopted in Göteborg on June 16, 2001;

- the Declaration and Implementation Plan, adopted at the UN World Summit on Sustainable Development in Johannesburg on September 4, 2002;

- the Declaration from the 5th Conference of Ministers of the Environment of the region of the UN Economic Commission for Europe, "An Environment for Europe" in Kiev on May 23, 2003.

Financing of the individual tasks of the Action Plan remains an unresolved aspect. Allocations from European social funds could become an important new source. For the period following accession to EU, support for EEA and Local Agendas 21 has been prepared at ME in cooperation with MLSA from the funds of the European Social Fund in the framework of measures of EEA and public participation in protection of the environment in the Operational Program of Development of Human Resources (more information is available from the External Relations Department of ME). Further potential for financing the Action Plan follow from Decision No. 466/2002/EC of the European Parliament and Council, establishing a Community action program of support for NGOs active particularly in the area of protection of the environment (more information is available from the External Relations Department of ME or at the web site http://europa.eu.int/comm/environment/funding/finansup.htm).

This publication includes not only the test of the Action Plan for 2004 - 2006, but also the original text of the State Program of EEA (including the relevant Government Resolutions), additional updated addresses of organizations active in EEA, a survey of related laws and Government Resolutions, a survey of Regional Conceptions of EEA, etc. We are convinced that these annexes with the current information will at least partly make up for the deficit arising from the fact that SP EEA is three years old and logically contains information that is no longer up-to-date.

Although SP EEA is a Government document, its implementation requires extensive public participation, partners in the area of business entities, NGOs, the public administration, and others. We would like to thank especially the members of the International EEA Working Group at ME, the persons preparing the regional EEA conceptions, all engaged NGOs, the responsible employees of the public administration, entrepreneurs and a great many others for cooperation in carrying out the tasks of the Action Plan for 2001 - 2003. We are convinced that cooperation will continue at the same level during future important stages, in 2004 - 2006.

THE GOVERNMENT OF THE CZECH REPUBLIC

RESOLUTION

OF THE GOVERNMENT OF THE CZECH REPUBLIC

of October 8, 2003 No. 991 + P

to implement Government Resolution 1048/2000 on the State Program of Environmental Education and Public Awareness in the Czech Republic

The Government

I. takes into cognisance the Report on fulfilling of  Government Resolution 1048/2000 on the State Program of Environmental Education and Public Awareness in the Czech Republic, and its Annex - the Action Plan of the State Program of Environmental Education and Public Awareness in the Czech Republic for 2001 - 2003, contained in Part III of material ref. no. 1266/03;

II. approves the Action Plan of the State Program of Environmental Education and Public Awareness in the Czech Republic for 2004 - 2006, set forth in the Annex to this Resolution (hereinafter the "Action Plan");

III. requires that

1. the Minister of the Environment and the Minister of Education, Youth and Sports

a) cooperate in support for the activities of nongovernmental organizations in the area of environmental education and public awareness in the Czech Republic,

b) methodically influence the Regional systems of environmental education and public awareness in the Czech Republic,

2. the Members of the Government

a) in the framework of  the budgetary chapters of the sectors, provide for funds of an investment and noninvestment character for implementation of tasks following from the Action Plan,

b) methodically influence the activities of the Regional Authorities in the sense of the State Program of Environmental Education and Public Awareness in the Czech Republic,

c) provide personnel for fulfilling the tasks of the Action Plan,

3. the Minister of the Environment provide for publication of this Resolution in the Bulletin of the Government for the regional authorities and municipal authorities;

IV. recommends that the regional administrators, Lord Mayor of the Capital City of Prague, Lord Mayors of the statutory cities and mayors of municipalities with the authorized municipal authorities actively support and implement regional systems of environmental education and public awareness in the Czech Republic.

To be implemented by:

Members of the Government and heads of the other central bodies of the state administration

For information:

Regional Administrators, Lord Mayors of statutory cities

Prime Minister

PhDr. Vladimír  Š p i d l a,  in his own hand

Action Plan

State Program of Environmental Education and Public Awareness

in the Czech Republic for 2004 - 2006

(part of implementation of Directive 90/313/EEC on free access to information, which was replaced by Directive 4/2003/EC)

I. 	Cross-sectional measures

II. 	Education of employees in administrative authorities, officials in territorial self-governing units and elected members of municipal councils

III. 	Children, youth, pedagogical workers and professional workers

IV. 	Business and tertiary sphere

V. 	Information, enlightenment and consulting for the public

VI. 	Personnel and financial base for the State Program of Environmental Education and Public Awareness in the Czech Republic for 2004 - 2006

VII. 	Recommendations

I. Cross-sectional measures

1. Utilize the permanent intersectoral working group at the Ministry of the Environment as a consulting body for coordination, regular control and updating of the State Program of Environmental Education and Public Awareness in the Czech Republic (hereinafter SP EEA CR). The Minister of the Environment nominates, names and directs the intersectoral working group.

Deadline: on-going

Responsible: Minister of the Environment

Cooperation: Members of the Government and heads of the other central administrative bodies

2. Annual evaluation of fulfilling of the tasks of the Action Plan of SP EEA CR, including effective measures, as a special part of the Report on the Environment and also regularly for the individual measuresin accordance with the set dates for fulfillment.

Deadline: always to September 30 for the previous calendar year annually, i.e. by the end of September of the following year

Responsible: Minister of the Environment

Cooperation: Ministers of the relevant Ministries*)

Recommendation: cooperate in evaluation of fulfilling of the Action Plan of SP EEA CR with Associations of Regions, Federations of cities and municipalities of CR, universities, technical institutes, NGOs.

3. Support for regional and local EEA systems

a) creation of regional and local conceptions of EEA,

a) implementation of regional and local systems of EEA,

c) offer methodical assistance,

d) support awareness and cooperation of regions, cities and municipalities

Deadline: on-going

Responsible: Minister of the Environment and Minister of Education, Youth and Sports1)

Cooperation: Ministers of the relevant Ministries, regional administrators1), Lord Mayor of the Capital City of Prague, lord mayors and mayors of cities and municipalities2)

-----------------------------

1) § 13 (1), (2) and (3a) of Act No. 123/1998 Coll., on the right to environmental information, as amended by Act Bo. 132/2000 Coll., and also § 77a (3) (u) of CNC Act No. 114/1992 Coll., on protection of nature and the landscape, as amended, and § 16 of Act No. 17/1992 Coll., on the environment, as amended

2) § 2 (2) and § 66 of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

4. Elaborate, within their competence, the tasks of the Action Plan for 2004 - 2006 for SP EEA CR at the level of the central administrative authorities and territorial self-governing units.

Deadline: by June 30, 2004

Responsible: Members of the Government, heads of the other central administrative bodies

Cooperation:  regional administrators1), Lord Mayor of the Capital City of Prague, lord mayors and mayors of cities and municipalities2)

-----------------------------

1) § 13 (1), (2) and (3a) of Act No. 123/1998 Coll., on the right to environmental information, as amended by Act Bo. 132/2000 Coll., and also § 77a (3) (u) of CNC Act No. 114/1992 Coll., on protection of nature and the landscape, as amended, and § 16 of Act No. 17/1992 Coll., on the environment, as amended

2) § 2 (2) and § 66 of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

5. Take into account aspects of sustainable development in creation of the legislation.

Deadline: on-going

Responsible: Members of the Government and heads of the other central administrative bodies

Cooperation: Other persons submitting draft legislation.

6. Create conditions for possible public participation in all procedures related to protection of the environment and in preparation of new or amended laws, policies, budgets and conceptions, and provide for public awareness in accordance with Act No. 123/1998 Coll., on the right to information on the environment, as amended by Act No. 132/2000 Coll., and in accordance with international agreements.

Deadline: on-going

Responsible: Members of the Government and heads of the other central administrative bodies

Cooperation: Other persons submitting draft legislation.

7. Prepare and approve a conception of EEA for National Parks and the administrations of Protected Landscape Areas in the form of material taking into account SP EEA in CR (including the Action Plan) and the individual regional conceptions of EA.

Deadline: 30. June 2004

Responsible: Directors of the National Park Administrations, Director of the Administrations of the Protected Landscape Areas of the Czech Republic (hereinafter "Administrations of PLA CR")

Cooperation: Minister of the Environment, Director of the Czech Environmental Institute

8. Take into account the targets of SP EEA CR in creation and implementation of the other national and supranational programs.

Deadline: on-going

Responsible: Members of the Government and heads of the other central administrative bodies

Cooperation: regional administrators1), Lord Mayor of the Capital City of Prague2)

--------------------------

1) § 13 (1), (2) and (3a) of Act No. 123/1998 Coll., on the right to environmental information, as amended by Act Bo. 132/2000 Coll., and also § 77a (3) (u) of CNC Act No. 114/1992 Coll., on protection of nature and the landscape, as amended, and § 16 of Act No. 17/1992 Coll., on the environment, as amended

2) § 2 (2) and § 66 of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

9. Monitoring and targeted support for the joint program of ME and MEYS for the development of environmental education centres in an attempt to stabilise these facilities in each region. Representatives of the public administration, in whose regions the services are provided, are the main partners for the activities of the environmental education centres.

Deadline: on-going

Responsible: Minister of the Environment and Minister of Education, Youth and Sports

Cooperation: State Environmental Fund of the Czech Republic (hereinafter "SEF CR") and other state funds, authorities of the regions with delegated competence.

II. Education of employees in administrative authorities, officials of territorial self-governing units and elected members of municipal councils

10. Coordinate the education of employees in administrative authorities (with the exception of employees carrying out work of a technical and service character) in the subject of the environment and sustainable development utilising educational programs guaranteed and regularly updated by ME.

Deadline: during 2004 - 2005 and then on-going

Responsible: Head of the Office of the Government of the Czech Republic

11. Provide for the environmental education of employees in administrative authorities (with the exception of employees carrying out work of a technical and service character) through the offer of the Institute for State Administration utilising educational programs guaranteed and regularly updated by ME.

Deadline: during 2004 - 2005 and then on-going

Responsible: Head of the Office of the Government of the Czech Republic

12. Provide for the environmental education of employees in territorial self-governing units (with the exception of employees carrying out work of a technical and service character) in the subject of the environment and sustainable development, in accordance with the system of education of officials of territorial self-governing units3), utilising educational programs guaranteed and regularly updated in cooperation with ME.

-------------------------

3) § 20 of Act No. 312/2002 Coll., on the officials of territorial self-governing units and amending some Acts

Deadline: during 2004 - 2005 and then on-going

Responsible: Minister of the Interior

13. Provide support for research projects whose results in practice will facilitate and make more effective implementation of SP EEA CR and its targets. Concentrate especially on areas in which the level of environmental awareness is low and simultaneously implementation significantly affects the future and present state of the environment.

Deadline: on-going

Responsible: Ministers of the relevant Ministries*)

Cooperation: subordinate administrative authorities, professional institutes and institutions at the relevant ministries and individual professionals

14. Stabilise and methodically support a functional network of employees of the public administration entrusted with responsibility for EEA.

Deadline: 31. December 2004

Responsible: Members of the Government, heads of the other central administrative bodies, regional administrators1) and the Lord Mayor of the Capital City of Prague

------------------------

1) § 13 (1), (2) and (3a) of Act No. 123/1998 Coll., on the right to environmental information, as amended by Act Bo. 132/2000 Coll., and also § 77a (3) (u) of CNC Act No. 114/1992 Coll., on protection of nature and the landscape, as amended, and § 16 of Act No. 17/1992 Coll., on the environment, as amended

Cooperation: Minister of the Environment (methodical support), relevant ministries*) and their subordinate administrative authorities and professional institutes and institutions, lord mayors and mayors of cities and municipalities2)

------------------------

2) § 2 (2) and § 66 of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

15. Effective work with the public in the area, education and public awareness, create a system of education for employees and workers of institutions in the sector of ME, whose work includes work with the public (primarily, e.g. administration of large protected landscape areas, territorial authorities who will deliberate the Natura 2000 system, etc.).

Deadline: to December 31, 2004

Responsible: Minister of the Environment

Cooperation: Directors of: administrations of National Parks, Administrations of  PLA CR, SEF CR, Czech Hydrometeorological Institute , Silva Tarouca Landscape and Ornamental Gardening Research Institute, Czech Geological Service, Czech Geological Service - Geofond, Agency for Protection of Nature and the Landscape of the Czech Republic, Czech Environmental Inspection, Tomáš G. Masaryk Water Management Research Institute, Czech Environmental Institute

16. Utilise information and communications technology in creation of education programs of all types concerned with the area of the environment.

Deadline: on-going

Responsible: Minister of the Environment, Minister of Education, Youth and Sports, Minister of Informatics, Minister of the Interior and Head of the Office of the Government of CR

Cooperation: Ministers of the relevant Ministries*)

III. Children, youth, pedagogical workers and professional workers

17. Provide targeted support for further education of pedagogical workers for the area of environmental education and public awareness and sustainable development. For this purpose, utilise, e.g. developmental programs of further education of pedagogical workers.

Deadline: on-going

Responsible: Minister of Education, Youth and Sports

Cooperation: subordinate administrative authorities of MEYS

Recommended cooperation: University Deans

18. Take into account EEA in preparing a profile of graduates of university study programs for preparation of pedagogical workers.

Deadline: on-going

Responsible: Minister of Education, Youth and Sports

Cooperation: subordinate administrative authorities of MEYS

19. Formulate standard education of pedagogical workers in EEA on the basis of a minimal general base of knowledge and skills of pedagogical students in the area of the environment, sustainable development and environmental education:

a) in further education of managerial workers in education,

b) in further education of all pedagogical workers.

Deadline: 31. 12. 2004

Responsible: Minister of Education, Youth and Sports

Cooperation: subordinate administrative authorities of MEYS

Recommended cooperation: Faculties preparing teachers.

IV. Business and the tertiary sphere

20. Information, methodical or teaching support for the subject of environmental education in company programs.

Deadline: on-going

Responsible: Minister of the Environment, Minister of Agriculture, Minister of Health, Minister of Industry and Trade, Minister of Transport, Minister of Defence

Cooperation: relevant bodies of the territorial self-governing units, SEF CR and other state funds.

21. Support and promote the rules of environmentally sound agriculture, and the program for development of rural areas, provide information on the food safety policy and introduce the principles of sound behaviour towards the environment. Provide for enlightenment on the importance of directives and laws related to sustainable construction, sustainable transport, energy management, protection of the climate, the Framework Directive on water, etc. at a company level.

Deadline: on-going

Responsible: Ministers of the relevant Ministries*)

Cooperation: Minister of the Environment

22. Increase the professional level and improve the availability of information provided for complex awareness of the business public in the area of the environment, including training of professional workers for environmental consulting (with emphasis especially on entrepreneurs, small and medium-sized companies and cooperation with municipalities) in the regions in connection with the relationship between operation of a business and the environment.

Deadline: on-going

Responsible: Minister of Industry and Trade, Minister of Transport, Minister of Agriculture

Cooperation: relevant bodies of the territorial self-governing units

23. Increase the environmental component in educational requalification programs. Utilise external financial and professional resources in the preparation. In the framework of these programs, prepare and provide sample educational models for companies, suitable for the individual sectors and groups of workers.

Deadline: on-going

Responsible: Minister of the Environment, Minister of Agriculture, Minister of Industry and Trade, Minister of Transport, Minister of Defence, Minister for Regional Development

Cooperation: Ministry of Labour and Social Affairs, subordinate authorities and professional institutes and institutions of the Ministry of the Environment, Ministry of Agriculture, Ministry of Health, Ministry of Industry and Trade, Ministry of Transport, Ministry of Defence, Ministry for Regional Development

24. Create a program of systematic support for environmental education and public awareness (consumers, employees of local government, small and medium-sized enterprises) in the methods of environmental consulting.

Deadline: 30. 6. 2004

Responsible: Minister of the Environment

Cooperation: Minister of Industry and Trade, Minister of Agriculture, relevant bodies of the territorial self-governing units, Director of SEF CR and directors of other state funds.

V. Information, enlightenment and consulting for the public

25. Provide information on Local Agendas 21 (LA 21) and provide for enlightenment and consulting in the area of implementation of the principles of sustainable development at a local and regional level.

Deadline: on-going

Responsible: Minister of the Environment, Ministers of the relevant Ministries*) and the heads of the other central state administrative bodies

Cooperation: Director of the Czech Environmental Institute, relevant bodies of the territorial self-governing units

26. Provide information on the nonproductive function of agriculture and forestry and on agriculture, cultivation of forests and environmentally sound forest management. Train professionals and provide environmental consulting.

Deadline: on-going

Responsible: Minister of Agriculture, Minister of the Environment

Cooperation: subordinate administrative authorities and professional institutes and institutions of MA and ME, Kontrola ekologického zemědělství o.p.s. (Control of environmentally sound agriculture, p.b.s.)

27. Provide for constant enlightenment in the area of the environmental impact of transport and protection of the climate.

Deadline: on-going

Responsible: Minister of Transport

Cooperation: Minister of the Environment, subordinate administrative authorities and professional institutes and institutions of the Ministry of Transport and the Ministry of the Environment

28. Publish, promote and effectively distribute material on the subject of the environment and sustainable development. In implementation of SP EEA CR, increase cooperation with public television and radio, public awareness and cultural educational facilities in order to reduce the detrimental environmental impacts of consumer patterns based on consumption.

Deadline: on-going

Responsible: Minister of the Environment, Ministers of the relevant Ministries*) and the heads of the other central state administrative bodies

Cooperation: relevant bodies of the territorial self-governing units

29. Formulate conditions for the choice and support for targeted media campaigns, including granting and promoting awards, participation and presentations at exhibitions and trade fairs (devoted to various business spheres), etc. Participate in events promoting sound use of raw materials, energy and sound management of the landscape.

Deadline: on-going

Responsible: Minister of the Environment, Minister of Agriculture, Minister of Health, Minister of Industry and Trade, Minister of Transport, Minister of Defence

Cooperation: subordinate authorities and professional institutes and institutions of the Ministry of the Environment, Ministry of Agriculture, Ministry of Health, Ministry of Industry and Trade, Ministry of Transport, Ministry of Defence

30. In the framework of EEA, create scope for adopting of sound environmental tax reform in accordance with the principles of sustainable development so that their introduction is requested and favourably accepted by citizens.

Deadline: on-going

Responsible: Minister of the Environment

Cooperation: Ministers of the relevant Ministries*)

31. Create and introduce a system of voluntary labelling of products that would inform the consumer of the material and transport intensity of the given product in the framework of its life cycle or an important part thereof, and use a suitably chosen complex indicator (e.g. environmental track) to provide information on the overall environmental burden caused by a certain product. Incorporate the concept of sustainable consumption into the system.

Deadline: on-going

Responsible: 0{>Minister of Industry and Trade and Minister of the Environment

Cooperation: Ministers of the relevant Ministries*)

32. Targeted development of consulting work concerned with development of businesses, simultaneously complying with the principles of optimal exploitation of natural resources, especially renewable resources, environmental consulting activities in organisation of the state administration, small and medium-sized business entities and NGOs (including initiation of new audited activities and a certification system) under the assumption of high professionalism.

Deadline: on-going

Responsible: Minister of the Environment, Minister of Agriculture, Minister of Health, Minister of Industry and Trade, Minister of Transport, Minister of Defence, Minister for Regional Development, Minister of Labour and Social Affairs

Cooperation: Minister of Finance relevant bodies of the territorial self-governing units, SEF CR and other state funds.

33. Incorporation of environmental consulting in CR into the international network and international cooperation.

Deadline: on-going

Responsible: Minister of the Environment, Minister of Agriculture, Minister of Health, Minister of Industry and Trade, Minister of Transport, Minister of Defence, Minister of Labour and Social Affairs, Minister of Foreign Affairs

Cooperation: relevant bodies of the territorial self-governing units

VI. Provision of personnel and finances for SP EEA CR in 2004 to 2006

34. Establish positions for education, enlightenment and communication with the public at the central Administration of PLA CR and administrations of the individual PLA

Deadline: by the end of 2004 and then on-going

Responsible: Minister of the Environment

Cooperation: Director of the Administration of PLA CR and Directors of the Administrations of National Parks

35. Establish positions for education, enlightenment and communication with the public at the Ministry of Defence and Ministry of Transport.

Deadline: by the end of 2004 and then on-going

Responsible: Minister of Defence and Minister of Transport

36. Provide for conditions for functioning of a workplace fulfilling the function of coordination, information and consulting centre for EEA (in the framework of restructuring of the Czech Environmental Institute, provide for 7 positions by 2006, i.e. an increase by 2.5 positions).

Deadline: December 31, 2004 and then on-going

Responsible: Minister of the Environment

Cooperation: Director of the Czech Environmental Institute

37. Announce a program of support for projects concerned with EEA for educational and extracurricular activities.

Deadline: annually

Responsible: Minister of Education, Youth and Sports

Cooperation: Minister of the Environment, Ministers of the relevant Ministries*), regional administrators1), Lord Mayor of the Capital City of Prague, lord mayors and mayors of cities and municipalities2), state funds

-------------------------

1) § 13 (1), (2) and (3a) of Act No. 123/1998 Coll., on the right to environmental information, as amended by Act Bo. 132/2000 Coll., and also § 77a (3) (u) of CNC Act No. 114/1992 Coll., on protection of nature and the landscape, as amended, and § 16 of Act No. 17/1992 Coll., on the environment, as amended

2) § 2 (2) and § 66 of Act No. 128/2000 Coll.,  on municipalities (the municipal order), as amended.

38. In preparation of the state budget for the following year, the relevant ministries and central state administrative bodies shall incorporate the expected expenditures for SP EEA CR into the draft budget of the sectoral chapter. The regions should proceed similarly and incorporate the expected expenditures for SP EEA CR for the following year into their draft budgets. (As these are the internal funds of the regions and the activity is carried out by the region in independent competence; the central state administrative authorities cannot impose this obligation on them.) Financing of SP EEA CR must be ensured for both noninvestment expenditures and also for investment expenditures:

a) from their own budgetary sources, including use of rationalization measures,

b) proposal for increasing the budget from the funds of the state budget and from the regional budgets (funds lacking for everyday tasks),

b) proposal for increasing the budget from the funds of the state budget and from the regional budgets (for special tasks),

d) proposal for financing SP EEA CR shall be included by the central state administrative bodies in requests from state funds in CR and foreign sources.

Deadline: in accordance with the draft state budget for MF annually (for the regions, the draft regional budget)

Responsible: Minister of the Environment and Ministers of the relevant Ministries*), the heads of the other central state administrative bodies, regional administrators1), Lord Mayor of Capital City of Prague

--------------------------

1) § 13 (1), (2) and (3a) of Act No. 123/1998 Coll., on the right to environmental information, as amended by Act Bo. 132/2000 Coll., and also § 77a (3) (u) of CNC Act No. 114/1992 Coll., on protection of nature and the landscape, as amended, and § 16 of Act No. 17/1992 Coll., on the environment, as amended

Cooperation: Minister of Finance

39. In the framework of increasing budgets and rationalization measures, provide for the necessary financial means including funds for investments. The responsible and cooperating entities according to the Action Plan are responsible for providing for financing of SP EEA CR. The use of public contracts is also a suitable form. We recommend that a system of pooling of funds be employed. Media and other activities in work with the public should be financed from the chapters of the ministries (or administrative authorities), according to their competence.

Deadline: on-going

Responsible: Minister of the Environment and Ministers of the relevant Ministries*), the heads of the other central state administrative bodies and the relevant territorial self-governing unit authorities

Cooperation: SEF CR and other funds

40. Incorporation of the introduction of multi-annual financing into the conditions for subsidy support for NGOs for activities supported by the state (in the rules for provision of subsidies to NGOs from the state budget) and into the drafts for the relevant related laws.

Deadline: in accordance with the draft rules for provision of funds to NGOs

Responsible: Minister of the Environment, Minister of Finance and Ministers of the relevant Ministries*)

Cooperation: heads of the other central state administrative authorities, Government Council for NGOs, SEF CR and other state funds, relevant bodies of the territorial self-governing units

41. Search for, negotiate and utilise potential cooperation with support from foreign sources of assistance in financing EEA. Cooperate with the Ministry of Finance in creating the necessary conditions for financing of supranational programs or in carrying out the tasks of EEA following from international agreements.

Deadline: gradually, on-going

Responsible: Minister of the Environment and Minister of Education, Youth and Sports in cooperation with the Minister of Foreign Affairs

Cooperation: Minister of Finance, Ministers of the relevant Ministries*), the heads of the other central state administrative bodies

42. Prepare conditions for implementation of EEA projects supported from the funds of the European Union, e.g. in connection with the Sectoral Operation Plan for Development of Human Resources, the Joint Regional Operation Program - from the European Social Fund, etc.

Deadline: on-going

Responsible: Minister of Labour and Social Affairs, Minister of the Environment, Minister of Education, Youth and Sports

Cooperation: Ministers of the relevant Ministries*), the heads of the other central state administrative bodies and the relevant territorial self-governing unit authorities

43. Increase the provision of foreign developmental assistance in the area of education and public awareness in sustainable development in cooperation with the United Nations Organisation.

Deadline: on-going

Responsible: Minister of Foreign Affairs

Cooperation: Minister of the Environment, Minister of Education, Youth and Sports, Minister of Finance and Ministers of the other relevant Ministries*)

VII. Recommendations

44. Actively cooperate with the EEA intersectoral working group at ME and provide information for regular control of fulfilment and up-dating of SP EEA CR.

The recommendation is intended for: the regions, the Capital City of Prague, statutory cities4) and municipalities with extended competence

--------------------------

4) § 4 (1) of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

45. Initiate support for functioning of EEA consulting groups at the level of all the regions and, where possible, at the level of the cities, and prepare methodical recommendations for the EEA consulting groups at the level of the regions and cities.

The recommendation is intended for: the regions, the Capital City of Prague, statutory cities4) and municipalities with extended competence

--------------------------

4) § 4 (1) of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

46. Prepare the tasks of an Action Plan for 2004 - 2006 for SP EEA CR at all levels of the public administration.

The recommendation is intended for: the regions, the Capital City of Prague, statutory cities4) and municipalities with extended competence

--------------------------

4) § 4 (1) of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

47. Utilise special environmental minimum programs for education of elected officials at all levels of local government, especially for mayors.

Deadline: on-going, updated once annually

Cooperation: organisations subordinate to ME and MI

The recommendation is intended for: the regions, the Capital City of Prague, statutory cities4) and municipalities with extended competence

--------------------------

4) § 4 (1) of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

48. Provide for financial support for EEA in accordance with the regional conceptions of EEA and in the sense of SP EEA CR.

The recommendation is intended for: the regions, the Capital City of Prague, statutory cities4) and municipalities with extended competence

--------------------------

4) § 4 (1) of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

49. Incorporate environmental education and the subject of sustainable development into the study programs of all universities and other higher institutes of learning from the beginning of the 2004 - 2005 academic year (October 2004).

The recommendation is intended for: Rectors of universities and other higher institutes

50. Formulate standard education of pedagogical workers in EEA on the basis of a minimal general base of knowledge and skills of pedagogical students in the area of the environment, sustainable development and environmental education in pre-graduate preparation of all pedagogical workers.

The recommendation is intended for: Rectors of universities and other higher institutes of learning

-----------------------------

4) § 4 (1) of Act No. 128/2000 Coll., on municipalities (the municipal order), as amended.

Note:

*) For the purposes of this Resolution, the relevant Ministries means the Ministries that implement the tasks of SP EEA CR as specifically named in the Action Plan. The relevant ministries are: Ministry of the Environment (hereinafter "ME"), Ministry of Education, Youth and Sports (hereinafter MEYS), Ministry of the Interior (hereinafter MI), Ministry for Regional Development (hereinafter MRD), Ministry of Agriculture (hereinafter MA), Ministry of Transport (hereinafter MT), Ministry of Industry and Trade (hereinafter MIT), Ministry of Health (hereinafter MH), Ministry of Defence (hereinafter MD), Ministry of Culture (hereinafter MC), Ministry of Labour and Social Affairs (hereinafter MLSA), Ministry of Finance (hereinafter MF), Ministry of Informatics (hereinafter MIn) and Ministry of Foreign Affairs (hereinafter MFA).

Intersectoral Agreement

on Cooperation in the Area of Environmental Education and Public Awareness

between the Ministry of the Environment

and

the Ministry of Education, Youth and Sports

Preamble

The Ministry of the Environment and the Ministry of Education, Youth and Sports have agreed on a joint approach in providing for environmental education and public awareness (hereinafter EEA) in the Czech Republic, in connection with the legal force of Act No. 123/1998 Coll., on the right to information on the environment (in the sense of the provision of § 13 of this Act), in its currently valid wording, and in the sense of the State Program of Environmental Education and Public Awareness in the Czech Republic, approved by Government Resolution No. 1048 of October 23, 2000 and its tasks laid down in its Action Plan, up-dated in each case for the relevant year.

The Ministries have agreed that, beyond the framework of the above documents, they will:

- provide for mutual cooperation of the EEA sectoral working groups in preparing conceptual materials on the subject of environmental education and public awareness and utilizing the professional potential of the sectoral organizations, including the sectoral information systems,

- provide conceptual and strategic plans and documents to one another for the working commentary procedure, including those that are not the subject of an external commentary procedure, and utilize the employees of both sectors for consultations,

- in the framework of methodical and professional management, permanently support cooperation and regular exchange of information between the educational and environmental departments of the Regional Authorities in the area of EEA, sustainable development, in the programs of Chapter 36 of Local Agendas 21 and international programs,

- hold joint methodical workshops on special subjects for the regional employees of the state administration responsible for EEA,

- in the framework of announced programs, support the projects of nongovernmental organizations related to the environment in the sense of EEA and sustainable development, without respect to the size of their membership base, and provide for mutual provision of information on the progress of tender procedures and the contents of the supported projects. They shall provide one another with the outputs of these projects if this is useful for the partner Ministry,

- support the participation of Czech nongovernmental organizations in international projects related to EEA and the environment in the sense of sustainable development,

- announce programs to support nongovernmental organizations that systematically create networks in the area of EEA in the Czech Republic,

- reciprocally provide for the activities of professionals in tender commissions for pro projects in the area of EEA, sustainable development, the environment, Local Agendas 21 and the Lisbon process in the area of education,

- The Ministry of Education, Youth and Sports shall support the participation of pedagogical workers in workshops and events in the area of EEA, sustainable development, the environment, Local Agendas 21 and other international programs held, guaranteed or financed by the Ministry of the Environment,

- The Ministry of the Environment shall support efforts of the Ministry of Education, Youth and Sports in implementing and gradually introducing environmental education in the sense of sustainable development into the relevant laws and legislative regulations related to education, youth and sports, including further education of pedagogical workers.

Prague, February 5, 2004

(signed)	(signed)

JUDr. Petra Buzková	RNDr. Libor Ambrozek

Minister of Education, Youth and Sports	Minister of the Environment

Ecocentres of the Czech Union of  Nature Conservation (ČSOP)

Ústřední výkonná rada ČSOP

Uruguayská 7, 120 00  PRAHA 2

Tel.: 222 516 115, Fax: 222 511 496

E-mail: csop@ecn.cz

http://www.csop.ecn.cz

Ekostředisko mládeže JELENICE

Pozořice 332, 664 07  POZOŘICE

Tel.: 544 226 066
zřizovatel: 55/07 ZO ČSOP

Ekocentrum ZO ČSOP Rokycany

Švermova 748/II, 337 01  ROKYCANY
Tel./fax: 371 722 686
 zřizovatel: 29/01 ZO ČSOP

Ekocentrum ČSOP PODORLICKO

U Stadionu 602, 560 02  ČESKÁ TŘEBOVÁ

Tel.: 465 534 006, 465 535 762
zřizovatel: 52/01 ZO ČSOP

Středisko ochranářské výchovy Vodárenská věž

Na Výšinách 1000, 170 00  PRAHA 7
zřizovatel: 01/30 ZO ČSOP

Ekocentrum ČSOP CHALOUPKY

¨

Kněžice 109, 675 21  OKŘÍŠKY
Tel.: 568 870 434, Fax: 568 870 359
zřizovatel: 62/88 ZO ČSOP

Ekocentrum VIKŠTEJN

Dubová u Vítkova, RADKOV
Tel.: 553 713 531, 737 672 861
zřizovatel: 72/06 ZO ČSOP

Valašské Ekocentrum ČSOP

U Rajky 15, 757 01  VALAŠSKÉ MEZIŘÍČÍ
Tel./fax: 571 621 602
zřizovatel: 100/SmRS ČSOP

Centrum pro děti a mládež ČSOP

Dittrichova 9, 120 00  PRAHA 2
Tel.: 224 912 466, 606 900 286, Fax: 224 921 765
zřizovatel: 01/SMOP ČSOP

Terénní ekologické středisko BOŘÍ

Divoky, 768 02  ZDOUNKY
Tel.: 573 365 591
zřizovatel: 60/05 ZO ČSOP

Ekocentrum ČSOP Písek

Nová Ves 35, 398 31  ČÍŽOVÁ
Tel.: 606 885 810
zřizovatel: 18/08 ZO ČSOP Písek

Ekocentrum ČSOP Zelené Vendolí

Vendolí 42, 569 14  VENDOLÍ
Tel.: 461 593 235, 461 545 526
zřizovatel: 50/10 ZO ČSOP

Ekocentrum ČSOP Bílé Karpaty

Bartolomějské nám. 47, 698 01  VESELÍ nad Moravou
Tel.: 518 322 545, Fax: 518 324792
 zřizovatel: 58/06 ZO ČSOP

Ekocentrum ČSOP CEIS

Masná 131, 381 01  ČESKÝ KRUMLOV
Tel.: 380 704 620
zřizovatel: 15/06 ZO ČSOP

Ekocentrum ČSOP Velké Popovice

Farská 21, 251 69  VELKÉ POPOVICE
Tel.: 323 665 202, 323 665 206
zřizovatel: 10/02 ZO ČSOP

Ekocentrum ČSOP MAKOV

Nová Ves 10, 398 31  ČÍŽOVÁ
Tel.: 382 279 159, 728 130 527
zřizovatel: 18/02 ZO ČSOP

Ekocentrum ČSOP SEV "Aquila"

Bartošovice 146, 742 54  BARTOŠOVICE na Moravě
Tel./fax: 556 758 675
zřizovatel: 70/02 ZO ČSOP

Ekocentrum ČSOP JAROMĚŘ

Náměstí ČSA 38, 551 01  JAROMĚŘ 1
Tel.: 491 813 242
zřizovatel: 46/03 ZO ČSOP Osadníci

Ekocentrum ČSOP RADNICE

Na Potocích 221, 338 28  RADNICE 
Tel.: 724 077 208, Fax: 371 785 085
zřizovatel: 29/02 ZO ČSOP

Ekocentrum ČSOP KONIKLEC

Chelčického 12, 130 00  PRAHA 3 
Tel.: 222 712 189
zřizovatel: 01/71 ZO ČSOP Koniklec

Ekocentrum ČSOP ORLICE

Náhon 277, 500 09  HRADEC KRÁLOVÉ
Tel./fax: 495 261 587
zřizovatel: 43/01 ZO ČSOP Orlice

Ekocentrum ČSOP Iris

Husovo nám. 67, 796 01  PROSTĚJOV
Tel.: 582 338 278
zřizovatel: 61/RS ČSOP Prostějov

Informační středisko JIZERKA

Jizerka 43, 468 50  HORNÍ POLUBNÝ 
Tel.: 723 519 290, 602 154 228, Fax: 483 312 128
zřizovatel: 35/03 ZO ČSOP Jizerka

Stanice ekologické výchovy CICONIA

Máchova 1309, 413 01  ROUDNICE nad Labem 
Tel.: 416 837 603, 732 149 330
zřizovatel: 37/01 ZO ČSOP

Ekocentrum ČSOP CHODOVÁČEK

Nám. Míru 39, 357 35  CHODOV
Tel.: 728 507 059
 zřizovatel: 30/02 ZO ČSOP

Ekocentrum ČSOP STRAKONICE

Zámek 1, 386 01  STRAKONICE 
Tel.: 383 371 084, 383 332 108
zřizovatel: 20/01 ZO ČSOP

Stanice ochrany přírody PASÍČKA

Bor u Skutče 47, 539 44  PROSEČ 
Tel.: 469 321 396
zřizovatel: 44/03 ZO ČSOP

Středisko ekologické výchovy MRAVENEC

Pražská 1655, 393 01  PELHŘIMOV
Tel.: 565 322 091
zřizovatel: 17/01 ZO ČSOP

Ekocentrum ČSOP MRÁČEK Jaroměř

Areál nemocnice, Národní 83, 551 01  JAROMĚŘ 
Tel.: 603 847 189
zřizovatel: 46/04 ZO ČSOP

Ekocentrum JIŽNÍ MĚSTO

Květnového vítězství 1554, 149 00  PRAHA 4 
Tel.: 603 238 910, 267 915 887

Tel./fax: 267 915 888
zřizovatel: 01/44 ZO ČSOP

Ekocentrum ČSOP VOTICE

Husova 383, 259 01  VOTICE
Tel.: 317 813 866, Fax: 317 814 780
zřizovatel: 02/10 ZO ČSOP

Středisko ekologické výchovy ČSOP Areka

Horní nám. 48, 746 01  OPAVA

Tel./fax: 553 623 988
zřizovatel: 72/05 ZO ČSOP Areka

Podblanické ekocentrum ČSOP

Pláteníkova 264, 258 01  VLAŠIM
Tel./fax: 317 845 169, 317 845 965
zřizovatel: 02/09 ZO ČSOP

Ekocentrum ČSOP Poznáním k ochraně

Kokořínská 2/58, 182 00  PRAHA 8 
Tel.: 776 209 100
zřizovatel: 01/68 ZO ČSOP

Centrum ekologické výchovy ZVONEČEK

MtŠ Březovská ulice, 252 46  VRANÉ nad Vltavou 
Tel.: 257 762 036
zřizovatel: 11/11 ZO ČSOP Zvoneček

Ekocentrum ČSOP Spálené Poříčí

Plzeňská 55, 335 61  SPÁLENÉ POŘÍČÍ
Tel.: 371 594 842, Fax: 371 594 654
zřizovatel: 27/04 ZO ČSOP

Ekocentrum ČSOP PLANORBIS

Prusinovského 113, 767 01  KROMĚŘÍŽ

Tel./fax: 573 340 210
zřizovatel: 60/03 ZO ČSOP Planorbis

Centrum ekologické výchovy PÁLAVA

Náměstí 32, 692 01  MIKULOV 
Tel.: 519 513 399, Fax: 519 511 130
zřizovatel: 56/15 ZO ČSOP Pálava

Ekocentrum ČSOP JEŠTĚD

Bažantí 378/3, 460 01  LIBEREC 1 
Tel./fax: 485 108 344
zřizovatel: 36/01 ZO ČSOP Stezka

Severočeské centrum ochránců přírody Tilia

W.Churchilla 8, 400 01  ÚSTÍ nad Labem
Tel./fax: 475 209 922, 472 770 088
zřizovatel: 33/04 ZO ČSOP Tilia

Ekocentrum ČSOP Dům ochránců přírody

Panská 9, 602 00  BRNO
Tel.: 542 422 753, Fax: 542 422 777
zřizovatel: 54/RS Brno

Environmental Education Centres

of the Pavučina Network

Senovážné nám. 24, 116 47 PRAHA 1

Tel./fax: 234 621 386

E-mail: info@pavucina-sev.cz

http://www.pavucina-sev.cz

Praha

EKOLA Praha

- středisko ekologické výchovy

Petýrkova 1948, 148 00  Praha 4

Tel.: 267 914 322

E-mail: ekolapraha@volny.cz

Toulcův dvůr - Ekologické centrum

hl. m. Prahy, ZČ HB Botič

Kubátova 1/32, 102 00  Praha 10 - Hostivař

Tel./fax: 271 750 548

E-mail: botic@ecn.cz

http://www.toulcuvdvur.cz

Živá planeta - sdružení pro ekologickou

a etickou výchovu

Hrudičkova 2107, 148 00  Praha 4

Tel./fax: 272 942 467

E-mail: ziva.planeta@volny.cz

http://www.zivaplaneta.ecn.cz

__________

Central Bohemia Region

Křivoklátsko, o.p.s. - Informační

a vzdělávací středisko Budy

Náměstí Svatopluka Čecha 82, 270 23  Křivoklát

Tel./fax: 313 558 123

E-mail: is.krivoklat@pvtnet.cz

http://pvtnet.cz/www/is.krivoklat

02/09 ZO ČSOP Vlašim

Podblanické ekocentrum ČSOP

Pláteníkova 264, 258 01  Vlašim

Tel./fax: 317 845 169, 317 845 965

E-mail: vlasim@csop.cz

http://www.csop.cz

TOM Javory Černuc

- středisko ekologické výchovy

Černuc 167, 273 23  Černuc

Tel. 315 762 156, Fax: 315 762 146

E-mail: javory@volny.cz

http://www.sweb.cz/javory

__________

South Bohemian Region

Dřípatka - centrum ekologické výchovy, pracoviště SVIS MŠMT

Rumpálova 402, 383 01  Prachatice

Tel./fax: 388 317 806

E-mail: dripatka.svis.-msmt@mybox.cz

http://www.dripatka.cz

Centrum ekologické a globální výchovy Cassiopeia - ZČ HB Forest

Jizerská 4, 370 11  České Budějovice

Tel.: 385 520 951

E-mail: cassiopeiacb@volny.cz

http://mujweb.cz/www/cassiopeia

Šípek - 15/06 ZO ČSOP Český Krumlov

Gymnázium, Chvalšinka 112,

381 01  Český Krumlov

Tel./fax: 380 714 048

E-mail: sev.sipek@seznam.cz

http: //www.sipek.ckrumlov.cz

Pilsen Region

Ametyst - středisko ekologické výchovy

Koterovská 84, 323 00  Plzeň
Tel.: 377 542 021

E-mail: eva.chvojkova@sev-ametyst.cz

__________

Usti Region

SEVER - Středisko ekologické výchovy

1. ZŠ, Na Valech 53, 412 01  Litoměřice

Tel.: 416 734 838

E-mail: severltm@telecom.cz

http://www.sever.ecn.cz

__________

Liberec Region

Statutární město Liberec

Nám. Dr. Edvarda Beneše 1, 460 59  Liberec 1

Tel.: 485 243 463, Fax: 485 243 423

E-mail: koci.ales@magistrat.liberec.cz

http://www.liberec.cz

Společnost přátel přírody

Tř. Svobody 243/58, 460 15  Liberec 15

Tel./fax: 482 751 195

E-mail: spp@cmelak.cz

http://www.cmelak.cz

Suchopýr - Lesní školky, o.p.s.

Jizerská 110, 460 15  Liberec 15

Tel.: 486 131 623, 486 131 624

E-mail: suchopyr@volny.cz

Hradec Kralové Region

SEVER - Středisko ekologické výchovy

a etiky Rýchory

542 26  Horní Maršov

Tel.: 499 874 280, 499 874 326, Fax: 499 874 181

E-mail: sever@ecn.cz

http://www.sever.ecn.cz

Pracoviště Hradec Králové:

Kavčí Plácek 121, 500 02  Hradec Králové

Tel.: 495 580 319

__________

Pardubice Region

Ekocentrum Paleta

Štolbova 2665, 530 02  Pardubice

Tel./fax: 466 614 352

E-mail: ekocentrum@paleta.cz

http://www.paleta.cz/

__________

Vysočina Region

Chaloupky - středisko pro vzdělávání

a výchovu v přírodě, o.p.s.

Kněžice 109, 675 21  pošta Okříšky

Tel.: 568 870 434, Fax: 568 870 359

E-mail: info@chaloupky.cz

http://www.chaloupky.cz

__________

Southern Moravia Region

Lipka - Dům ekologické výchovy

Pracoviště Lipová 20, 602 00  Brno - Pisárky
Tel./fax: 543 211 264

E-mail: lipka@lipka.cz 
http://www.lipka.cz

Pracoviště Rozmarýnek

Rozmarýnová 6, 637 00  Brno - Jundrov
Tel.: 541 220 208

E-mail: rozmarynek@volny.cz 

Pracoviště SEV Rychta Krásensko

Krásensko 76, 683 07  Krásensko
Tel.: 517 385 429

E-mail: krasensko@lipka.cz

Rezekvítek - sdružení pro ekologickou výchovu a ochranu přírody

Kamenná 6, 639 00  Brno

Tel.: 543 216 483, Fax: 543 211 264

E-mail: rezekvitek@rezekvitek.cz

http://www. rezekvitek.cz

Centrum ekologické výchovy Pálava

Náměstí 32, 692 01  Mikulov

Tel.: 519 513 399, Fax: 519 511 130

E-mail: cev@palava.cz

http://www.palava.cz/cev

Vzdělávací a informační středisko

Bílé Karpaty, o.p.s.

Bartolomějské nám. 47,

698 01  Veselí nad Moravou

Tel.: 518 322 545, Fax: 518 324 792

E-mail: visbk@bilekarpaty.cz

http://www.bilekarpaty.cz/vis

__________

Zlin Region

ALCEDO - dům dětí a mládeže ve Vsetíně

Jiráskova 419, 755 01  Vsetín

Tel./fax: 571 617 704

E-mail: alcedo@vs.inext.cz

http://www.alcedo-vs.cz

Zelená školička - ZO ČSOP Javorníček

Zd. Fibicha 1203, 757 01  Valašské Meziříčí

Tel./fax: 571 622 243

E-mail: csopvm@quick.cz

KOSENKA

- ZO ČSOP a ekologická poradna

Brumovská 11, 766 11  Valašské Klobouky

Tel.: 577 320 069

E-mail: kosenka@mail.walachia.cz

Planorbis - 60/03 ZO ČSOP

Vrchlického 2859, 767 01  Kroměříž

Tel./fax: 573 340 210

E-mail: planorbis@naucnastezka.cz

http://www.naucnastezka.cz/planorbis

ASTRA - DDM Zlín

Tyršovo nábřeží 801, 760 01  Zlín

Tel./fax: 577 271 311, 577 142 742

E-mail: ddmpriluky@volny.cz

__________

Olomouc Region

Sluňákov

- sdružení pro ekologickou výchovu

Magistrát města Olomouce,

Horní náměstí 1, 771 27  Olomouc

Tel.: 585 513 225, 585 513 222, Fax: 585 513 271

E-mail: slunakov@mmol.cz http://www.olomoucko.cz/slunakov

Vila Doris

- Středisko ekologické výchovy při DDM

ul. 17. listopadu 2, 787 01  Šumperk

Tel.: 583 214 212-3, Fax: 583 214 214

E-mail: vila @doris.cz

http://www.doris.cz

__________

Moravian-Silesian Region

Vita - občanské sdružení

Gen. Janouška 4, 702 00  Ostrava

Tel./fax: kancelář  596 616 155,

ekologická poradna  596 611 158,

středisko ekologické výchovy  596 639 863

E-mail: info@vitaova.cz

http://www.vitaova.cz

Hájenka - středisko ekologické výchovy

Janíkovo sedlo 36, P. O. BOX 17,

742 21  Kopřivnice
Tel.: 604 526 114

E-mail: dalis@centrum.cz

__________

Observers:

Borudo - občanské sdružení

Donín 120, 463 34  Hrádek nad Nisou

Tel.: 604 717 726

E-mail: borudo@borudo.org

Beskydčan, Ostravice

Muchovice 393, 739 14  Ostravice

E-mail: beskydcan@raz-dva.cz

Ještěr - ZČ Hnutí Brontosaurus

Husova 191, 790 01  Jeseník

Tel.: 584 429 316

E-mail: jester@brontosaurus.cz

Středisko volného času Hodonín

Jilemnického 2, 695 03  Hodonín

Tel.: +420 518 321 502

E-mail: ekocentrum.hodonin@seznam.cz

Společnost Renata

Pod Kaštany 28, 616 00  Brno

Tel.: +420 603 350 026

E-mail: spol.renata@volny.cz, http://www:volny.cz/spol.renata

Eco – Counselling Network (STEP)

Office Brno

Síť ekologických poraden
Panská 9, 602 00  Brno 
Tel.: 542 422 758

Office Ostrava

Síť ekologických poraden 
Ahepjukova 2, 702 00  Ostrava 
Tel.: 596 623 212 nebo 603 449 385 
E-mail: step@ecn.cz 
http://www.ekoporadna.cz

Members

Ekologický právní servis

Bratislavská 31, 602 00  Brno 
Tel.: 545 214 431 
E-mail: brno@eps.cz

Vita - občanské sdružení

Generála Janouška 4, 702 00  Ostrava 
Tel.: 596 611 158 
E-mail: vitaova@ova.comp.cz

Podblanické ekocentrum

ČSOP Vlašim, Pláteníkova 264, 258 01  Vlašim 
Tel.: 317 845 169 
E-mail: vlasim@csop.cz

Zelený kruh

Lublaňská 18, 120 00  Praha 2 
Tel.: 222 518 352 
E-mail: zk@ecn.cz

ZO ČSOP Kosenka

Brumovská 11, 766 01  Valašské Klobouky 
Tel.: 0636 / 320069 
Fax: 0636 / 320145 
E-mail:kosenka@mail.walachia.cz 
http://www.kosenka.cz, www.zachranles.cz

ROSA - jihočeská společnost 
pro ochranu přírody, o.p.s.

Nádražní 55, 370 01  České Budějovice 
Tel.: 387 432 030 
E-mail: rosa@ecn.cz

Středisko ekologické výchovy 
a etiky Rýchory SEVER

542 26 Horní Maršov 
Tel.: 499 874 280 
E-mail: sever@ecn.cz

ZO ČSOP Veronica

Panská 9, 602 00  Brno 
Tel.: 542 422 750 
E-mail: veronica@ecn.cz

Vzdělávací a informační 
středisko Bílé Karpaty

Bartolomějské náměstí 47,

698 01  Veselí nad Moravou 
Tel.: 518 322 545 
E-mail: visbk@bilekarpaty.cz