Action Plan for Implementing the Convention on Biological Diversity’s

Programme of Work on Protected Areas

(MOZAMBIQUE)

Submitted to the Secretariat of the Convention on Biological Diversity [30 of March, 2012]

Protected area information:

PoWPA Focal Point: Felismina Atanásio Longamane Langa

Fax: +258 21 302373

Mobile phone: +258 821530270

Email: felisminal@yahoo.com.br/flongamane@gmail.com

Ministry of Tourism,

National Directorate for Conservation Areas

Av. 10 de Novembro, Praceta 1196, nº 40, Maputo

Lead implementing agency:

Ministry of Tourism, Through the National Directorate for Conservation Areas

Multi-stakeholder committee:

Under the legislation there are Management Councils (MC) for each protected area. The MC  are composed by all stakeholders in the area. Public, private sector, NGOs, local communities’ representantives. The MC has the responsibility to support the day by day management of the Park. They use the management plan as the guiding instrument (/tool)

At National Level the Government established the Commission for Facilitation of Tourism. This commission is composed by various Government Departments. It discusses and recommends to Government various issues related with the development of tourism including management of protected areas. Cases of proclamation, modification of limits of protected areas as well as the concessioning of tourism in PA are discussed and recommended actions from this Commission. Particularly the Transfrontier Conservation Areas Program has used this commission to get policy guidance.

There is a Conservation working Group (CWG) composed by Government Agencies, NGO’s and Donors, interested in the natural resources conservation. Sometimes, private sector is invited for some discussions. The CWG meets once a month and it has been established as a forum of sharing information on protected areas and providing technical support to PA’s.

At the level of the Council of Ministers, there is a Council for sustainable development (CONDES) that oversees all the aspects linked to environment and development.

Description of protected area system

# National Targets and Vision for Protected Areas

(Insert national targets for protected areas/Target 11 of the Aichi Targets. Include rationale from protected area gap assessment, if completed, along with any additional information about the vision for the protected area system, including statements about the value of the protected area system to the country)

VISION

The Vision of the Government is the  establishment of a sustainably  funded  representative system of  protected areas under an effective  management regime.

TARGETS

Create buffer zones around Parks and Reserves to enable adaptation in areas surrounding conservation areas, otherwise PAs will become unsustainable islands

Expand Protected areas system by creating new areas and expanding others such as Banhine National Park and Zinave National Park, to include important habitats that are not actually covered.

Establish corridors to improve ecological integrity between Limpopo , Banhine and Zinave National Parks. These 3 parks are part of the greater Limpopo transfrontier  park, and the establishment of corridors between them is important because they will allow the maintenance of the historic migratory patterns of wildlife, specially elephants, that usually migrate from one area to another seeking water and other resources.

Train all park managers, field rangers and all staff at local level in other to strengthen their capacity to manage natural resources for climate resilience and adaptation, to communicate the value of ecosystems and protected areas in climate change resilience and adaptation and to incorporate climate issues into biodiversity management plans.

Restore the vegetation of Gorongosa Mountain (from 700 meters up) and at least restored 50% of hydrological systems that feeds the Lake Urema, considered the heart of Gorongosa National Park, that is drying up.

Establish transfrontier conservation areas between Mozambique, Zambia and Zimbabwe and between Mozambique and Tanzania to maintain the functions of ecosystems and allow the migration of animals between Selous Game Reserve in Tanzania and Niassa Reserve in Mozambique, and between animals from Tchuma Tchato community area and Zimbabwe and Zambia. Conduct evaluation studies in two protected areas and establish local management committees at site-level to improve governance

Coverage

Mozambique has a network of protected areas that covers all eco-regions and biomes ensuring their integrity as a representative portion of the natural legacy of the country.  The currently gazetted PAs estate covers 13 million hectares, which represents  about 25 % of the country’s land surface, of which about 5% are marine protected areas.

The national protected areas system comprises 48 areas designated for the conservation of flora and fauna. These are:

(1) six National Parks, of which two are coastal/marine protected areas (MPAs), including, Bazaruto (143,000 hectares exclusively marine) Quirimbas (750,639 hectares); and the terrestrial parks of Banhine, Gorongosa, Limpopo and Zinave (together with 2,775,000 hectares);

(2); 8 National Reserves (Gilé, Marromeu, Niassa, Maputo, Chimanimani and Pomene, Partial Reserve of Niassa Lake (478 km² and Marine Partial Reserve of Ponta de Ouro (MPA with 600 Km²) totalling more than 4,580,000 hectares);

(3) 15 controlled hunting concessions (or Coutadas with at least 4,675,000 hectares); and

(4) Thirteen Forest Reserves (comprehending 532,000 hectares).

Description and background

Although most Protected areas were established before 1975, in the last  two decades Mozambique’s Protected areas systems has known positive developments, with expansion of Niassa Reserve  and Bazaruto National Park in the late 90’s , the creation of Limpopo National Park (2001),  Quirimbas National park (2002), Chimanimani National Reserve (2003), 3 hunting areas (2009/2010), Marine Partial Reserve of Ponta de Ouro (2009), Expansion of Maputo Special Reserve, with the establishment of Futi Corridor, Lake Niassa Partial Reserve (2011), Expansion of Gorongosa National Park, to include Gorongosa Mountain and creation of Buffer Zone (2010), Creation of Buffer zone around Gile Reserve (2011), establishment of ecological corridor between Limpopo National Park and Banhine National Park, establishment of 3 transfrontier conservation areas. Currently, most of the areas have management plans.

Governance types

Two protected areas are co-managed by state with private sector, Coutadas are managed by private sector through concession’s contracts, 8 protected areas are managed by State with donor support and the rest are managed by State. They are also community programmes such as Tchuma Tchato in Tete Province and Chipanje Tcheto in Niassa Province.

Areas like Limpopo National Park, Zinave National Park, Banhine National Park, Quirimbas National park, Chimanimani Reserve, Gile Reserve, Maputo Reserve and Ponta de Ouro Marine Partial Reserve have steering committees  (government, donors, NGOs) that meet 4 times a year to oversee the implementation of working plans and discuss other relevant aspects related to the areas. Some areas such as Quirimbas, Niassa, Zinave and Banhine have also committees formed by local government, DNAC and local communities that also meet twice a year to follow the working plan and advise when necessary.

According to the Conservation Policy approved in 2009, each protected area must have at site-level, a management committee composed by the Park Warden, representatives of the provincial and district levels, local communities, NGOs operating in the area and private sector.

Key threats

Institutional weakness: associated to the lack of human, financial and material resources to ensure sustainability of the system.

Poor operational levels of management due to lack of field and adequate equipment and materials

Poaching, affecting areas such as Niassa Reserve, Quirimbas Park, Limpopo Park, Maputo Reserve, involving  species like important species like elephants,.

Growth of demand, in the domestic market, of firewood in cities and od specific natural resources such as prime woods, animals and products of endangered animals (e.g rhinoceros horns) in international markets, whose demand fosters illegal exploitation of resources above the natural replacement capacity of relevant resources. mining activities within and around Gorongosa National park, Chimanimani Reserve, and other protected areas.

Shifting agriculture in area that have human communities within them

Increase in domestic stock outcompeting wildlife which numbers can dangerously be in sharp decrease due to high intensity of poaching

Subsistence activities due the existence of high numbers of humans inside protected areas

Barriers for effective implementation

Lack of financial and human resources is the main barrier for effective implementation

For instance:

- Lack of  vehicles and field equipment and other field tools like 2 man tents, uniforms, first aid kits, GPS, inter alia.

- Lack of adequate training of staff from field abilities and techniques to thinking/planning ability

- Money to carry out ecological monitoring, i.e, aerial census, vegetation monitoring, human use of the resources

- Lack of adequate qualified human resources to carry out the activities properly

5. Different institutions involved in the management of different types of protected areas (Ministry of Tourism, Agriculture, Fisheries, culture, defense, Transport and communications).

Status, priority and timeline for key actions of the Programme of Work on Protected Areas

# Status of key actions of the Programme of Work on Protected Areas

| Status of key actions of the Programme of Work on Protected Areas | Status |
| --- | --- |
| - Progress on assessing gaps in the protected area network (1.1) | 3 |
| - Progress in assessing protected area integration (1.2) | 4 |
| - Progress in establishing transboundary protected areas and regional networks (1.3) | 3 |
| - Progress in developing site-level management plans (1.4) | 3 |
| - Progress in assessing threats and opportunities for restoration (1.5) | 2 |
| - Progress in assessing equitable sharing of benefits (2.1) - Progress in assessing protected area governance (2.1) | 3 |
| - Progress in assessing the participation of indigenous and local communities in key protected area decisions (2.2) | 4 |
| - Progress in assessing the policy environment for establishing and managing protected areas (3.1) - Progress in assessing the values of protected areas (3.1) | 4 |
| - Progress in assessing protected area capacity needs (3.2) | 4 |
| - Progress in assessing the appropriate technology needs (3.3) | 3 |
| - Progress in assessing protected area sustainable finance needs (3.4) | 4 |
| - Progress in conducting public awareness campaigns (3.5) | 3 |
| - Progress in developing best practices and minimum standards (4.1) | 4 |
| - Progress in assessing management effectiveness (4.2) | 4 |
| - Progress in establishing an effective PA monitoring system (4.3) | 3 |
| - Progress in developing a research program for protected areas (4.4) | 2 |
| - Progress in assessing opportunities for marine protection | 4 |
| - Progress in incorporating climate change aspects into protected areas | 3 |

Status: 0 = no work, 1 = just started, 2 = partially complete, 3 = nearly complete, 4 = complete

# Priority actions for fully implementing the Programme of Work on Protected Areas:

| Nº | Activity | Timeline |
| --- | --- | --- |
| 1 | Elaboration of Conservation Law | 2012 |
| 2 | Establishment of ecological corridors between Banhine National Park, Zinave National park and Gonarhezou Park | 2015 |
| 3 | Development of human capital (Field Rangers, Park Warden and other senior staff) | 2018 |
| 4 | Creation of New Conservation Areas (Coutadas de Caça and marine protected areas) | 2018 |
| 5 | Creation of Transfrontier Conservation Areas between Mozambique, Zambia and Zimbabwe and between Mozambique and Tanzania | 2015 |
| 5 |  |  |
| 65 | Ponta do Ouro Marine Partial Reserve declared as World Heritage Site | 2015 |
| 6 | Revision of boundaries of Protected area, namely Banhine National Park and Zinave National Park, Niassa Reserve | 2015 |
| 8 |  |  |
| 7 | Conduct mining impacts evaluation Studies in Conservation Areas . The case of Gorongosa National park and Chimanimani Reserve, due the mining concessions in the buffer zone and illegal mining | 2015 |
| 8 | Conduct evaluation study in the Maputo Special Reserve/Ponta de ouro Marine Partial Reserve, due the proposed marine Port at Techobanine area | 2015 |
| 9 | Create local management committees at site level | 2013 |
| 10 | Integration of Climate Change Aspects in the management plans | 2016 |
| 11 | Establishment of Mahlazine ecological Park | 2015 |
| 12 | Elaboration od biodiversity strategy and fifth national report | 2015 |

# Action Plans for completing priority actions of the Programme of Work on Protected Areas

Action 1: (Elaboration of Conservation Law)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Submission the the council of Ministers for approval | 2012 | Ministry of Tourism (MITUR) |  |
| Submission to the Parliament | 2013 |  |  |

Action 2: (Establishment of ecological corridors between Banhine National Park, Zinave National park and Gonarhezou Park)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Tender Launching |  |  |  |
| Selection of individual or company | 2013 | Ministry of Tourism , Ministry of Agriculture (MINAG) | 5.000 |
| Elaboration of Management plan | 2015 | Ministry of Tourism, Ministry of Agriculture | 200.000 USD |
| Implementation of management plan | 2020 | Parks managers/local communities | 100.000 |

Action 3: (Development of human capital - Capacity building of Game rangers, Park Warden, Senior Managers)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Identification of training needs | 2012 | MITUR , Ministry for Coordination of Environmental Affairs (MICOA), MINAG | 5.000 |
| Elaboration of Training program | 2012 | MITUR, MICOA, MINAG | 10.000 |
| Training | 2013-2018 | Ministry of tourism, Universities, trainers | 200.000 |

Action 4: (Creation of New Conservation Areas (Coutadas de Caça)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Social and ecological surveys | 2013 | National Directorate for Conservation Areas (DNAC), Tourism Provincial Directorate | 50.000 |
| Discussions with local communities and local government | 2013-2014 | Tourism Provincial Directorate/DNAC | 15.000 |
| Presentation at Provincial level | 2014 | Tourism Provincial Directorate | 5.000 |
| Submission to the Council Ministers for approval | 2014 | MITUR | - |

Action 5: (Creation of Transfrontier Conservation Areas between Mozambique, Zambia and Zimbabwe and between Mozambique and Tanzania-2015 )

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Discussions at the provincial level |  | MITUR/Provincial directorate of Tourism |  |
| Discussions with the Zambia and Zimbabwe | 2012-2015 | MITUR |  |
| Discussions with Tanzania | 2012-2015 | MITUR |  |
| Signature of MoU | 2015 | MITUR |  |
| Signature of Treaty | 2016 | MITUR |  |

Action 6: (Revision of the boundaries of Protected areas, namely Banhine National Park and Zinave National Park and Niassa Reserve)

| Key steps |  | Timeline |  | Responsible parties | Indicative budget |
| --- | --- | --- | --- | --- | --- |
| Consultation with local communities |  | 2012 |  | MITUR |  |
| Presentation at provincial level |  | 2012 |  | MITUR |  |
| Submission to the Council of Ministers | 2012-2013 |  | MITUR |  |  |

Action 7: (Conduct Mining impacts evaluation Studies. The case ofthe Gorongosa National Park and Chimanimani Reserve due the mining concessions in the buffer zone and illegal mining)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Development of Terms of reference | 2013 | Park manager/MITUR | 500 |
| Tender and selection of the company that will conduct the study | 2013 | Park manager/MITUR | 3.000 |
| Development of methodology | 2013 | Company selected/park manager/MITUR |  |
| Evaluation of GNP and Chimanimani | 2014 | Selected company | 200.000 |
| Communication of Results | 2015 | Park manager/Provincial directorate of Tourism | 10.000 |
| Public Awareness and education | 2017 | Park manager/provincial directorate of Tourism/MITUR | 50.000 |

Action 8: (Conduct evaluation study in the Maputo Special Reserve/Ponta de Ouro Marine Partial Reserve due the proposed marine Port at Techobanine area)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Development of Terms of reference | 2013 | Park manager/MITUR | 500 |
| Tender and selection of the company that will conduct the study | 2013 | Park manager/MITUR | 3.000 |
| Development of methodology | 2013 | Company selected/park manager/MITUR |  |
| Evaluation of Maputo Reserve | 2014 | Selected company | 100.000 |
| Communication of Results | 2015 | Park manager/Provincial directorate of Tourism | 10.000 |

Action 9: (Create local management committees at site level )

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Identification of interested stakeholders in the area | 2012 | Park manager |  |
| Organization of local communities committees | 2013 | Park manager |  |
| Creation of protected area management committee | 2013 | Park manager/Provincial Directorate of Tourism |  |

Action 10: (Integration of Climate Change Aspects in the management plans)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Tender and selection of the company that will conduct the study | 2013 | MITUR | 3.000 |
| Development of methodology | 2013 | Company selected/park manager/MITUR |  |
| Elaboration of management plans for Marromeu and Pomene Reserves | 2013-2014 | Selected company/ MITUR | 100.000 |
| Approval of the plans | 2015 | MITUR |  |
| Implementation of REDD+ pilot project in Moribane and mocuburi forests reserves | 2016 | MICOA |  |

Action 11: (Establisment of Mahlazine Ecological Park)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Landmines cleaning | 2012/2013 | Ministry of Foreing Affairs and Cooperation (MNEC), Ministry of Coordination of Environmental Affairs (MICOA) and Ministry of Defense (MDN) | 4.500.000 |
| Viability Study | 2013 | MICOA/MITUR/Maputo Municipality | 100.000 |
| Construction of Infrastructures (veterinary hospital, offices, military museum, | 2015 | MICOA /MITUR/ Maputo Municipality | 2.500.000 |

Action 12: (Elaboration of biodiversity strategy and fifth national report)

| Key steps | Timeline | Responsible parties | Indicative budget |
| --- | --- | --- | --- |
| Preparation of Terms of reference |  | MICOA |  |
| Selection of Company |  | MICOA |  |
| Elaboration of Biodiversity Strategy and Fifth National Report | 2015 | MICOA |  |