Chapter 5

ACTION PLAN

FOR BIODIVERSITY IN ROMANIA

121

ACTION PLAN FOR BIODIVERSITY IN ROMANIA

Action Plan for Biodiversity in Romania includes the objectives, sub-objectives and actions in relation to the responsible institutions, type of ownership in some cases, and the estimated necessary budget funding sources and the performance indicators for each action. e matrix as a whole is broken down into 10 objectives, 15 sub-objectives and a total 179 actions.

Fig. 5.1 shows the number of activities for 2012 – 2020. Note that for 2012-2014 the strategy has scheduled a sgni"cantly higher (about 50 – 60%) number of activities to be conducted.

A review of individual actions or of the overall budget allocation, of more than 1 billion EUR overall, indicates three categories of actions:

- 6 actions where the necessary budget could not be directly assessed or estimated, and where this will be done as the measures are implemented by the responsible institutions;

- 128 actions not requiring a direct budget, based on the stakeholder institutions or organisations implementing those actions as part of their normal activities, or using volunteers;

- 45 actions where the budgets were assessed based on various criteria, including:

- Assessment per unit of space (area – ha , length – km);

- Assessment per unit of time (year);

- Assessment per type of activity or target area (study, locality);

- Necessary budget for the entire action over the entire period; noting that this category includes budget estimates of a broad range, from EUR 150 million/ action to EUR 20 thousand/ action (depending on the size or complexity of that measure).

Advanced financial assessments of the strategy were based on the following justifications:

- experience of similar previous actions in the country or abroad;

- Preliminary calculations based on specific technical-economic indicators.

Fig. 5.1 Annual breakdown of activity numbers

122

123

| Table 5.1. Action Plan for Biodiversity în România |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Responsible |  | Period | Budget | Funding | Priority | Reporting |
|  |  | institutions |  |  | (EUR) | sources |  | indicators |
| A. | DEVELOPMENT OF THE GENERAL LEGISLATIVE AND INSTITUTIONAL FRAMEWORK AND SECURING OF FINANCIAL RESOURCES |  |  |  |  |  |  |  |
| A.1 | Establish a separate budget line for bio- | MEF |  | 2012 – 2012 | - | Own | Urgent | Achieved/ not |
|  | diversity conservation under the central |  |  |  |  | resources |  | achieved |
|  | environmental public authority |  |  |  |  |  |  |  |
| A.2 | Improvement of the legal framework to | MEF |  | 2012 – 2012 | - | Own | High | Achieved/ not |
|  | include additional penalties for failure to |  |  |  |  | resources |  | achieved |
|  | comply with all the legal provisions on |  |  |  |  |  |  |  |
|  | biodiversity conservation |  |  |  |  |  |  |  |
| A.3 | Strengthened enforcement of the legal | NEG, MAI |  | 2012 – 2020 | - | Own | High | Number of o$ences |
|  | framework on biodiversity conservation |  |  |  |  | resources |  | identi%ed |
| A.4 | Integration of the biodiversity conserva- | Local |  | 2012 – 2013 | - | Own | Medium | No. of plans |
|  | tion considerations into the regional and | government |  |  |  | resources |  | integrating |
|  | local policies, strategies, and plans | authorities |  |  |  |  |  | biodiversity |
|  |  |  |  |  |  |  |  | conservation |
|  |  |  |  |  |  |  |  | considerations |
| A.5 | Improved implementation of Priority | MEF |  | 2012 | - | Own | High | Achieved/ not |
|  | Axis 4 of SOP Environment |  |  |  |  | resources |  | achieved |
| A.6 | Revised categories of activities, appli- | MEF, EF |  | 2012 | - | Own | Urgent | Achieved/ not |
|  | cants, eligible expenses and funding |  |  |  |  | resources |  | achieved |
|  | mechanisms in the Environmental Fund |  |  |  |  |  |  |  |
|  | Funding Guidelines |  |  |  |  |  |  |  |
| A.7 | Diversi%cation of income sources feeding | MEF, EF |  | 2012 – 2020 | - | Own | High | % of revenue |
|  | the Environmental Fund |  |  |  |  | resources |  | increase |
| A.8 | Allocation of 20% of the Environmental | MEF, EF |  | 2012 – 2020 | - | Own | High | % allocated |
|  | Fund revenues for biodiversity conserva- |  |  |  |  | resources |  |  |
|  | tion activities |  |  |  |  |  |  |  |

124

| table continued |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions |  |  |  | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  |  |  | institutions |  | (EUR) | sources |  | indicators |
| A.9 | Providing co-!nancing to LIFE+ Nature |  |  |  | MEF, EF | 2012 – 2020 | - | Own | High | No. of co-funded |
|  | and Biodiversity from the Environmental |  |  |  |  |  |  | resources |  | projects |
|  | Fund |  |  |  |  |  |  |  |  |  |
| A.10 | Establishing | the | necessary | !nancial | MEF | 2012 – 2012 | 200,000 | State | Medium | No. of mechanisms |
|  | mechanisms to supplement the revenues |  |  |  |  |  |  | Budget |  | set up |
|  | from the state budget allocated for biodi- |  |  |  |  |  |  |  |  |  |
|  | versity conservation and the management |  |  |  |  |  |  |  |  |  |
|  | of the natural protected area network |  |  |  |  |  |  |  |  |  |
| A.11 | Creating the necessary legal framework |  |  |  | MEF | 2012 | - | Own | Low | Achieved/ not |
|  | to summarise the results of biodiversity |  |  |  |  |  |  | resources |  | achieved |
|  | conservation projects funded from public |  |  |  |  |  |  |  |  |  |
|  | sources |  |  |  |  |  |  |  |  |  |
| A.12 | Large-scale application of the results |  |  |  | MEF | 2012 – 2020 | - | Own | Medium | No. of conservation |
|  | obtained in successful projects funded |  |  |  |  |  |  | resources |  | measures |
|  | from European funds for nature |  |  |  |  |  |  |  |  | replicated |
|  | protection (e.g. Phare, LIFE, SOP |  |  |  |  |  |  |  |  |  |
|  | –Environment, etc.) |  |  |  |  |  |  |  |  |  |
| A.13 | Study of the contribution of natural pro- |  |  |  | MEF | 2012 – 2013 | 500,000 | State | Low | Achieved/ not |
|  | tected areas to the national economy |  |  |  |  |  |  | Budget |  | achieved |
| A.14 | Special fund earmarked for partial co- |  |  |  | MEF | 2012 – 2020 | 1,000,000/ | Environ- | Low | No. of funded |
|  | !nancing of NGO-proposed projects |  |  |  |  |  | year | mental |  | projects |
|  |  |  |  |  |  |  |  | Fund |  |  |
| A.15 | Cost estimate for the implementation |  |  |  | MEF | 2012 – 2013 | 1,000,000 | State | High | Achieved/ not |
|  | of community interest species and |  |  |  |  |  |  | Budget |  | achieved |
|  | habitat conservation measures for co- |  |  |  |  |  |  |  |  |  |
|  | !nancing and submittal to the European |  |  |  |  |  |  |  |  |  |
|  | Commission |  |  |  |  |  |  |  |  |  |

125

| table continued |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  | institutions |  | (EUR) | sources |  | indicators |
| A.16 | Development of a transparent funding | MEF | 2012 – 2012 | 200,000 | State | High | Achieved/ not |
|  | strategy for the necessary activities in |  |  |  | Budget |  | achieved |
|  | implementing the EU nature protection |  |  |  |  |  |  |
|  | Directives (from both the state budget |  |  |  |  |  |  |
|  | and other sources) |  |  |  |  |  |  |
| A.17 | Establishment of a counter-expertise | MEF | 2012 – 2012 | 1,000,000 | Environ- | Medium | No. of expert |
|  | fund to be used by the environmental |  |  |  | mental |  | studies |
|  | authorities issuing regulatory documents |  |  |  | Fund |  |  |
|  | based on the appropriate impact |  |  |  |  |  |  |
|  | assessment procedure |  |  |  |  |  |  |
| A.18 | Development and adoption of the National | MEF, ARD, | 2012 – 2015 | - | Own | Low | Achieved/ not |
|  | Programme of Ex Situ Conservation | MERYS |  |  | resources |  | achieved |
| A.19 | Setting up a couter-aluation fund acces- | MEF | 2012 – 2012 | 1,000,000 | Environ- | Medium | No. of valuations |
|  | sible to the regulation-issuing environ- |  |  |  | mental |  | performed |
|  | mental authorities under the adequate |  |  |  | Fund |  |  |
|  | assessment procedure |  |  |  |  |  |  |
| B. | PROVIDING CONSISTENCY AND EFFICIENT MANAGEMENT OF THE NATIONAL PROTECTED AREA NETWORK |  |  |  |  |  |  |
| B.1 | Re-establishment and development of the | Government, | 2012 | 3,000,000 | State | Urgent | Achieved/ not |
|  | ANAP, establishment of a similar institu- | MEF |  |  | Budget, |  | achieved |
|  | tional body in charge of coordinating the |  |  |  | own funds |  |  |
|  | management of natural protected areas, |  |  |  |  |  |  |
|  | including regional/ local structures |  |  |  |  |  |  |
| B.2 | Amended legal framework on the com- | MEF | 2012 | - | Own | Urgent | Achieved/ not |
|  | pulsory endorsement of plans, projects |  |  |  | resources |  | achieved |
|  | and activities that may impact the species |  |  |  |  |  |  |
|  | and natural habitats of conservation con- |  |  |  |  |  |  |
|  | cern by the administrators/ custodians |  |  |  |  |  |  |
|  | of the natural protected areas of national |  |  |  |  |  |  |
|  | and international importance |  |  |  |  |  |  |

126

| table continued |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions |  |  |  |  | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  |  |  |  | institutions |  | (EUR) | sources |  | indicators |
| B.3 | Improve | the | contract | provisions | for | MEF | 2012 | - | Own | Urgent | Achieved/ not |
|  | the administration/ custody of natural |  |  |  |  |  |  |  | resources |  | achieved |
|  | protected areas |  |  |  |  |  |  |  |  |  |  |
| B.4 | Development and adoption of a frame- |  |  |  |  | MEF | 2012 | - | Own | High | Achieved/ not |
|  | work content of management plans of all |  |  |  |  |  |  |  | resources |  | achieved |
|  | the categories of natural protected areas |  |  |  |  |  |  |  |  |  |  |
| B.5 | Providing a minimal level of funds from |  |  |  |  | MEF, RNP | 2012 – 2020 | 14,000,000/ | State | Urgent | Annually allocated |
|  | the state budget for the management of |  |  |  |  |  |  | year | Budget |  | amount |
|  | natural protected areas |  |  |  |  |  |  |  |  |  |  |
| B.6 | Development and adoption of technical |  |  |  |  | MEF | 2012 | - | Own | Medium | Achieved/ not |
|  | norms for forest managements and the |  |  |  |  |  |  |  | resources |  | achieved |
|  | management of forests within the natural |  |  |  |  |  |  |  |  |  |  |
|  | protected areas |  |  |  |  |  |  |  |  |  |  |
| B.7 | Establishing regulations to give priority |  |  |  |  | MEF | 2012 – 2012 | - | Own | Medium | Achieved/ not |
|  | to the re-naturalisation of ecological |  |  |  |  |  |  |  | resources |  | achieved |
|  | systems |  |  |  |  |  |  |  |  |  |  |
| B.8 | Development and adoption of the regula- |  |  |  |  | MEF | 2012 | - | Own | High | Achieved/ not |
|  | tions on waste management responsibili- |  |  |  |  |  |  |  | resources |  | achieved |
|  | ties outside localities in the natural pro- |  |  |  |  |  |  |  |  |  |  |
|  | tected areas |  |  |  |  |  |  |  |  |  |  |
| B.9 | Establishment and adoption of regula- |  |  |  |  | MEF, MRDT | 2012 | - | Own | Urgent | Achieved/ not |
|  | tions harmonising the land use develop- |  |  |  |  |  |  |  | resources |  | achieved |
|  | ment, urbanism and heritage protection |  |  |  |  |  |  |  |  |  |  |
|  | legislation with those on natural protect- |  |  |  |  |  |  |  |  |  |  |
|  | ed areas |  |  |  |  |  |  |  |  |  |  |
| B.10 | Approval of local zoning regulations in |  |  |  |  | MEF, MRDT | 2012 | - | Own | Urgent | Achieved/ not |
|  | natural protected areas |  |  |  |  |  |  |  | resources |  | achieved |

127

| table continued |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions |  |  |  | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  |  |  | institutions |  | (EUR) | sources |  | indicators |
| B.11 | Establishment of administrators/ custo- |  |  |  | MEF | 2012 | - | Own | Urgent | No. of natural pro- |
|  | dians for all the natural protected areas |  |  |  |  |  |  | resources |  | tected areas taken |
|  |  |  |  |  |  |  |  |  |  | in administration/ |
|  |  |  |  |  |  |  |  |  |  | custody |
| B.12 | Establishment of legal procedures for the |  |  |  | MEF | 2012 – 2020 | 150,000,000 | State | Medium | ha of private land |
|  | purchase of private land by the state, in |  |  |  |  |  |  | Budget, EF, |  | purchased by the |
|  | areas of strict protection regime within |  |  |  |  |  |  | LIFE+ |  | state |
|  | natural protected areas |  |  |  |  |  |  |  |  |  |
| B.13 | Assessment of natural habitats and wild |  |  |  | MEF | 2012 | 1,000,000 | State | Urgent | Acceptance by the |
|  | species of community importance in !- |  |  |  |  |  |  | Budget |  | EC of the Roma- |
|  | nalising designation of the Natura 2000 |  |  |  |  |  |  |  |  | nian Natura 2000 |
|  | Network in Romania |  |  |  |  |  |  |  |  | Network |
| B.14 | Mapping the distribution of natural |  |  |  | MEF, MERYS | 2012 – 2012 | 5,000,000 | State | Urgent | No. of natural |
|  | habitats and habitats of the wild species |  |  |  |  |  |  | Budget, |  | habitats and wild |
|  | of conservation concern |  |  |  |  |  |  | SOP Env. |  | species of conser- |
|  |  |  |  |  |  |  |  | EF |  | vation concern |
|  |  |  |  |  |  |  |  |  |  | mapped |
| B.15 | Analysis of the coherence of natural |  |  |  | MEF | 2012 – 2013 | - | Own | Medium | Achieved/ not |
|  | protected | areas, | including | ecological |  |  |  | resources |  | achieved |
|  | corridors |  |  |  |  |  |  |  |  |  |
| B.16 | Development of background studies and |  |  |  | MEF, research | 2012 – 2020 | 500,000 | State | Medium | % of protected |
|  | designation of new natural protected |  |  |  | and education |  |  | Budget |  | areas designated of |
|  | areas and ecological corridors |  |  |  | institutions, |  |  |  |  | the necessary total |
|  |  |  |  |  | NGOs |  |  |  |  |  |
| B.17 | Design and implementation of the |  |  |  | MEF | 2012 – 2020 | 1.5-2 | State Bud- | High | Monitoring system |
|  | national monitoring system under the |  |  |  |  |  | million/ | get, SOP |  | adopted and imple- |
|  | Habitats Directive |  |  |  |  |  | year | Env. EF |  | mented |

128

| table continued |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  | institutions |  | (EUR) | sources |  | indicators |
| B.18 | Design and implementation of natural | MEF | 2012 – 2020 | 1,000,000/ | State | High | No. of protected |
|  | protected area monitoring systems |  |  | year | Budget, EF |  | areas implement- |
|  |  |  |  |  |  |  | ing monitoring |
|  |  |  |  |  |  |  | systems |
| B.19 | Design of conservation measures as a | MEF | 2012 – 2013 | 200,000 | State | High | No. of species/ |
|  | basis for compensation payments for |  |  |  | Budget |  | habitats with con- |
|  | Natura 2000 |  |  |  |  |  | servation measures |
|  |  |  |  |  |  |  | established |
| B.20 | Calculation of amounts allocated as com- | MEF, MARD | 2012 – 2013 | 300,000 | State | High | No. of species/ |
|  | pensation payments under Natura 2000 |  |  |  | Budget |  | habitats with |
|  | based on the conservation measures set |  |  |  |  |  | compensation pay- |
|  | for each type of natural habitat and wild- |  |  |  |  |  | ments established |
|  | life species of community importance |  |  |  |  |  |  |
| B.21 | Payment of compensation to the land | MARD, | 2012 – 2013 | 100 million | State | High | % of total amount |
|  | users who comply with the restrictions | APDRP, MEF, |  |  | Budget, |  | paid to the |
|  | under Natura 2000 site requirements | Natura 2000 |  |  | EFARD |  | landowners |
|  |  | site admin- |  |  |  |  |  |
|  |  | istrators/ |  |  |  |  |  |
|  |  | custodians |  |  |  |  |  |
| B.22 | Payment of compensation to the forest | MARD, | 2012 – 2013 | 16.1 mil- | State | High | % of total amount |
|  | users who comply with the restrictions | APDRP, MEF, |  | lion | Budget, |  | paid to the |
|  | under Natura 2000 site requirements | Natura 2000 |  |  | EFARD |  | landowners |
|  |  | site admin- |  |  |  |  |  |
|  |  | istrators/ |  |  |  |  |  |
|  |  | custodians |  |  |  |  |  |
| B.23 | Payment of compensation to the forest | MEF | 2012 – 2020 | 5,000,000/ | State | High | % of total amount |
|  | owners who comply with the harvest- |  |  | year | Budget, |  | paid to the |
|  | ing restrictions in forests with protective |  |  |  | EFARD |  | landowners |
|  | functions of national interest (T1, T2) |  |  |  |  |  |  |

129

| table continued |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Actions |  |  |  |  |
| B.24 | Development and adoption of the mana- |  |  |  |  |
|  | gement plans for the natural protected |  |  |  |  |
|  | areas |  |  |  |  |
| B.25 | Assessment of the necessary management |  |  |  |  |
|  | plan implementation costs |  |  |  |  |
| B.26 | Updated study of old growth forests, re- |  |  |  |  |
|  | view and inclusion thereof in natural pro- |  |  |  |  |
|  | tected areas, preferably in areas of strict |  |  |  |  |
|  | protection regime |  |  |  |  |
| B.27 | Revised boundaries of the Retezat and |  |  |  |  |
|  | Pietrosul Rodnei biosphere reserves |  |  |  |  |
| B.28 | Designation of new protected areas of |  |  |  |  |
|  | international interest, (Ramsar sites, bio- |  |  |  |  |
|  | sphere reserves, world heritage sites). |  |  |  |  |
| B.29 | Harmonisation | of | the | transboundary |  |
|  | protected area | management measures |  |  |  |
|  | with those of the neighbouring countries |  |  |  |  |
| B.30 | Training among administrators and |  |  |  |  |
|  | custodians for implementing best adap- |  |  |  |  |
|  | tive management of natural protected |  |  |  |  |
|  | areas |  |  |  |  |
| B.31 | Development of volunteer network for |  |  |  |  |
|  | biodiversity monitoring |  |  |  |  |

| Responsible | Period | Budget | Funding | Priority | Reporting |
| --- | --- | --- | --- | --- | --- |
| institutions |  | (EUR) | sources |  | indicators |
| MEF, ad- | 2012 – 2020 | 9,000,000 | State | Urgent | No. of approved |
| ministrators/ |  |  | Budget, |  | management plans |
| custodians |  |  | SOP Env. |  |  |
|  |  |  | EF |  |  |
| administra- | 2012 – 2014 | - | Own | High | Achieved/ not |
| tors/ custodi- |  |  | resources |  | achieved |
| ans of natural |  |  |  |  |  |
| protected areas |  |  |  |  |  |
| MEF | 2012 – 2013 | 500,000 | State | Medium | Area of old growth |
|  |  |  | Budget |  | forests included in |
|  |  |  |  |  | natural protected |
|  |  |  |  |  | areas |
| MEF, RNP | 2012 | 20,000 | RNP, exter- | Medium | Achieved/ not |
|  |  |  | nal funds |  | achieved |
| MEF | 2012 – 2020 | - | Own | Medium | New PA of interna- |
|  |  |  | resources |  | tional importance |
|  |  |  |  |  | designated |
| MEF, adminis- | 2012 – 2013 | 600,000 | PA admin- | Medium | No. of PA with |
| trators |  |  | istrators, |  | common manage- |
|  |  |  | SOP Env., |  | ment measures |
|  |  |  | trans- |  | established |
|  |  |  | boundary |  |  |
|  |  |  | programs |  |  |
| MEF, adminis- | 2012 – 2015 | 500,000 | SOP Env. | High | % of trained sta! |
| trators/ custo- |  |  | SOP HRD |  |  |
| dians, NGOs |  |  |  |  |  |
| MEF | 2012 – 2020 | 200,000/ | State | Medium | No. of monitoring |
|  |  | year | Budget, EF |  | schemes |

130

| table continued |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions |  |  |  |  |  | Budget |  |
|  |  |  |  |  | Responsible | Period |  |  |
|  |  |  |  |  | institutions |  | (EUR) |  |
| B.32 | Evaluation of PA management e!cacy |  |  |  | MEF, ad- | 2012 – 2020 | - |  |
|  |  |  |  |  | ministrators/ |  |  |  |
|  |  |  |  |  | custodians |  |  |  |
| B.33 | Establishment of the Speological Heritage |  |  |  | MEF, NGO | 2012 | - |  |
|  | Commission |  |  |  |  |  |  |  |
| B.34 | Establishing | the | cavity | classi"cation | MEF, RSF | 2012 | - |  |
|  | norms in implementing EGO 57/ 207 on |  |  |  |  |  |  |  |
|  | the regime of protected natural areas, the |  |  |  |  |  |  |  |
|  | conservation of natural habitats and wild |  |  |  |  |  |  |  |
|  | !ora and fauna as amended |  |  |  |  |  |  |  |
| B.35 | Classi"cation of all cavities and establish- |  |  |  | MEF, adminis- | 2012-2020 | 80,000/ |  |
|  | ment of the legal status, by law |  |  |  | trators/ custo- |  | year |  |
|  |  |  |  |  | dians, NGOs |  |  |  |
| B.36 | Providing visitor infrastructure in some |  |  |  | administra- | 2012 – 2020 | 4,500,000 |  |
|  | cavities for educational purposes, for the |  |  |  | tors/ custo- |  |  |  |
|  | protection of local ecosystems |  |  |  | dians, NGOs, |  |  |  |
|  |  |  |  |  | local govt. |  |  |  |
| B.37 | Providing a special protection regime for |  |  |  | MEF | 2012 – 2012 | 50,000 |  |
|  | the IFLs |  |  |  |  |  |  |  |
| C. |  |  |  |  |  |  |  |  |
|  | PROVIDING GOOD SPECIES CONSERVATION STATUS OF PROTECTED WILDLIFE |  |  |  |  |  |  |  |
| C.1 |  |  |  |  |  |  | - |  |
|  | Updating the annexes of EGO 57/ 2007 |  |  |  | MEF | 2012 – 2015 |  |  |
|  | listing species of national interest |  |  |  |  |  |  |  |
| C.2 | Development and adoption of speci"c |  |  |  | MEF, AR, | 2012 – 2012 | 200,000 |  |
|  | regulations and the appropriate institu- |  |  |  | MERYS |  |  |  |
|  | tional framework to ensure good con- |  |  |  |  |  |  |  |
|  | servation status to the strictly protected |  |  |  |  |  |  |  |
|  | species of community importance and to |  |  |  |  |  |  |  |
|  | protected species of national interest out- |  |  |  |  |  |  |  |
|  | side natural protected areas |  |  |  |  |  |  |  |

| Funding | Priority | Reporting |  |
| --- | --- | --- | --- |
| sources |  | indicators |  |
| Own | Medium | Results available |  |
| resources |  | through the CHM |  |
| Own | Medium | Achieved/ not |  |
| resources |  | achieved |  |
| Own | Medium | Achieved/ not |  |
| resources |  | achieved |  |
| State | Medium | No. of classi"ed |  |
| Budget, EF |  | cavities |  |
| SOP Env., | Medium | No. of protected/ |  |
| Leader |  | developed cavities |  |
| EF | High | Achieved/ not |  |
|  |  | achieved |  |
|  |  | Achieved/ not |  |
| Own | Medium |  |  |
| resources |  | achieved |  |
| State | High | No. of species |  |
| Budget |  | regulated |  |

131

| table continued |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  | institutions |  | (EUR) | sources |  | indicators |
| C.3 | Development and updating of the Na- | MEF, MERYS | 2012 – 2020 | 1,500,000 | State | High | No. of lists devel- |
|  | tional Red Lists and Books of wild !ora |  |  |  | Budget |  | oped/ updated |
|  | and fauna |  |  |  |  |  |  |
| C.4 | Adoption, through a legal instrument, of | MEF | 2012 – 2020 | - | Own | High | No. of lists adopted |
|  | the National Red Lists of wild !ora and |  |  |  | resources |  |  |
|  | fauna |  |  |  |  |  |  |
| C.5 | Setting up legal mechanisms allowing | MEF, NEG | 2012 | - | Own | High | Achieved/ not |
|  | costs of repatriation of con"scated spe- |  |  |  | resources |  | achieved |
|  | cies and of maintaining them before re- |  |  |  |  |  |  |
|  | patriation to be borne by the o#enders/ |  |  |  |  |  |  |
|  | criminals |  |  |  |  |  |  |
| C.6 | Establishment of 5 special centres to | MEF, NEG, | 2012 – 2013 | 2,600,000 | State | High | No. of centres |
|  | house con"scated wildlife, based on a | NGO |  |  | Budget, EF |  |  |
|  | feasibility study to establish their loca- |  |  |  |  |  |  |
|  | tions and structure |  |  |  |  |  |  |
| C.7 | Designation and set up of mechanisms | MEF, MERYS, | 2012 – 2012 | - | Own | Low | Achieved/ not |
|  | allowing the environmental and customs | RA |  |  | resources, |  | achieved |
|  | authorities to identify specimens of pro- |  |  |  | State |  |  |
|  | tected species harvested/ captured, pro- |  |  |  | Budget |  |  |
|  | cured or traded, or parts thereof in live |  |  |  |  |  |  |
|  | and processed forms |  |  |  |  |  |  |
| C.8 | Implementation of mechanisms allowing | MEF | 2013 – 2020 | 100,000/ | State | Low | No. of cases solved |
|  | the environmental and customs authori- |  |  | year | Budget |  |  |
|  | ties to identify specimens of protected |  |  |  |  |  |  |
|  | species harvested/ captured, procured or |  |  |  |  |  |  |
|  | traded, or parts thereof in live and pro- |  |  |  |  |  |  |
|  | cessed forms |  |  |  |  |  |  |

132

| table continued |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  | institutions |  | (EUR) | sources |  | indicators |
| C.9 | Review of the conservation status of pro- | MEF, MERYS, | 2012 – 2012 | 250,000 | State | High | List of species for |
|  | tected species and selection of species | RA |  |  | Budget |  | the development of |
|  | requiring National Conservation Action |  |  |  |  |  | Action Plans |
|  | Plans (NSCAPs) |  |  |  |  |  |  |
| C.10 | Development of NSCAPs for the identi- | MEF, MERYS, | 2012 – 2015 | 5,000,000 | EF, | High | No. of action plans |
|  | !ed priority species | RA, NGO |  |  | external |  |  |
|  |  |  |  |  | funds |  |  |
| C.11 | Implementation of NSCAPs for 15 of the | MEF, adminis- | 2013 – 2020 | Not | State | High | No. of |
|  | priority species | trators/ custo- |  | estimated | Budget, EF |  | implemented plans |
|  |  | dians, NGOs, |  |  |  |  |  |
|  |  | scienti!c bod- |  |  |  |  |  |
|  |  | ies, universi- |  |  |  |  |  |
|  |  | ties, etc. |  |  |  |  |  |
| C.12 | Development of NSCAPs for medium | MEF, MERYS, | 2015 – 2020 | 5,000,000 | EF, exter- | Medium | No. of NSCAPs |
|  | priority species | RA, NGO |  |  | nal funds |  |  |
| C.13 | Rati!cation of AEWA amendments | MEF, MEA | 2012 | - | Own | High | Achieved/ not |
|  |  |  |  |  | resources |  | achieved |
| C.14 | Rati!cation of EUROBATS amendments | MEF, MEA | 2012 | - | Own | High | Achieved/ not |
|  |  |  |  |  | resources |  | achieved |
| D. | SUSTAINABLE USE OF BIOLOGICAL DIVERSITY COMPONENTS |  |  |  |  |  |  |
| D.1 | Assessment and establishment of the eco- | MEF | 2012 – 2013 | 1,000,000 | State | Medium | Biodiversity com- |
|  | nomic value of biodiversity components |  |  |  | Budget, EF, |  | ponents with value |
|  | and ecosystem services |  |  |  | external |  | estimations |
|  |  |  |  |  | funds |  |  |
| D.2 | Development and adoption of methodo- | MEF | 2014 – 2016 | 50,000 | State | High | No. of developed |
|  | logies to include the value of biodiversity |  |  |  | Budget, EF, |  | and approved |
|  | in the cost/ bene!t analyses of the feasi- |  |  |  | external |  | methodologies |
|  | bility studies and business plans |  |  |  | funds |  |  |

133

| TABLE CONTINUED |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions |  |  |  | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  |  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | D.3 | Development and adoption of eco-label- |  |  |  | MEF | 2012 – 2012 | 500,000 (?) | State | Medium | No. of Eco-label- |
|  |  | ling schemes based on the lifecycle analy- |  |  |  |  |  |  | Budget, EF, |  | ling schemes |
|  |  | sis of products that may a!ect biodiver- |  |  |  |  |  |  | external |  |  |
|  |  | sity by their manufacturing, distribution, |  |  |  |  |  |  | funds |  |  |
|  |  | use or storage |  |  |  |  |  |  |  |  |  |
|  | D.4 | Establishing incentives for the sustainable |  |  |  | MEF | 2012 – 2013 | 50,000 | State | Medium | No. of useful |
|  |  | use of biodiversity components and |  |  |  |  |  |  | Budget, EF, |  | incentives, no. of |
|  |  | removal of those with a negative impact |  |  |  |  |  |  | external |  | discarded incen- |
|  |  |  |  |  |  |  |  |  | funds |  | tives |
|  | D.5 | Establishment and adoption of the na- |  |  |  | MEF | 2012 – 2012 | 800,000 | State | High | Achieved/ not |
|  |  | tional Plan for wetland and degraded area |  |  |  |  |  |  | Budget, EF, |  | achieved |
|  |  | restoration |  |  |  |  |  |  | external |  |  |
|  |  |  |  |  |  |  |  |  | funds |  |  |
|  | D1. | LAND-USE DEVELOPMENT |  |  |  |  |  |  |  |  |  |
|  | D1.1 | Adoption of an architectural policy in |  |  |  | MRDT, OAR, | 2012 | - | Own | Urgent | Achieved/ not |
|  |  | Romania stressing on the culture of a na- |  |  |  | MCNH, MEF |  |  | resources |  | achieved |
|  |  | tural and built environment and the qua- |  |  |  |  |  |  |  |  |  |
|  |  | lity of life |  |  |  |  |  |  |  |  |  |
|  | D1.2 | Implementation of provisions on land- |  |  |  | MEF | 2012 | - | Own | High | Achieved/ not |
|  |  | scape and natural heritage into the legis- |  |  |  |  |  |  | resources |  | achieved |
|  |  | lation in force |  |  |  |  |  |  |  |  |  |
|  | D1.3 | Updating Appendix III to Law No. 5/ |  |  |  | MEF, MRDT, | 2012 | - | Own | High | Achieved/ not |
|  |  | 2000 on and use development, revision |  |  |  | MCNH |  |  | resources |  | achieved |
|  |  | of Article 7 to establish implementation |  |  |  |  |  |  |  |  |  |
|  |  | deadlines and penalties |  |  |  |  |  |  |  |  |  |
|  | D1.4 | Clari"cation | of | responsibilities | and | MEF, MRDT | 2012 – 2012 | - | Own | High | Achieved/ not |
|  |  | competences in enforcing punishments |  |  |  |  |  |  | resources |  | achieved |
|  |  | for non-compliance with discipline in |  |  |  |  |  |  |  |  |  |
|  |  | building |  |  |  |  |  |  |  |  |  |

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | D1.5 | Development of Landscape Identi"cation | OAR | 2012 | 300,000 | EF, exter- | High | Achieved/ not |
|  |  | and Assessment Guidelines |  |  |  | nal funds, |  | achieved |
|  |  |  |  |  |  | OAR |  |  |
|  | D1.6 | Inventory and assessment of cultural, nat- | MEF, MRDT | 2012 – 2015 | 1,500,000 | OAR, ROP, | High | % of the country |
|  |  | ural and mixed landscapes in Romania |  |  |  | Axis 5.1 |  | area inventoried |
|  |  |  |  |  |  |  |  | and assessed |
|  | D1.7 | Classi"cation of natural, cultural and | MEF, OAR | 2013 – 2014 | - | Own | Medium | In % of total land- |
|  |  | mixed landscapes of national importance |  |  |  | resources |  | scapes inventoried |
|  | D1.8 | Development of regulations for the man- | MEF, OAR | 2015 – 2020 | 500,000 | OAR, own | Medium | No. of regulations |
|  |  | agement of natural, cultural and mixed |  |  |  | resources |  | completed |
|  |  | landscapes |  |  |  |  |  |  |
|  | D1.9 | Development of local policies on land- | EPAs, local | 2015 – 2020 | - | Own | Medium | No. of local govt. |
|  |  | scape and integration with the other local | govt. au- |  |  | resources |  | authorities inte- |
|  |  | sectoral policies | thorities, OAR |  |  |  |  | grating landscape |
|  |  |  | branches |  |  |  |  | policies with land |
|  |  |  |  |  |  |  |  | use development |
|  | D1.10 | Development of a natural and cultural | SOP MAs | 2012 | - | Own | High | No. of SOPs |
|  |  | landscape impact assessment procedure |  |  |  | resources |  | integrating the |
|  |  | for projects funded from Structural and |  |  |  |  |  | obligation to |
|  |  | Cohesion Funds to accept for funding |  |  |  |  |  | preserve the |
|  |  | only projects that do not impact the land- |  |  |  |  |  | landscape |
|  |  | scape |  |  |  |  |  |  |
|  | D1.11 | Action plans for the reconstruction and/ | MEF, MRDT | 2015 – 2020 | - | Own | Medium | % of degraded/ |
|  |  | or restoration of degraded and/ or ruined |  |  |  | resources |  | ruined landscape |
|  |  | landscapes |  |  |  |  |  | area for which |
|  |  |  |  |  |  |  |  | action plans are |
|  |  |  |  |  |  |  |  | developed |

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | D1.12 | Studies to identify and assess species and | Local govt. | 2012 – 2015 | 15,000/ | Local bud- | Medium | No. of localities |
|  |  | their habitats in the urban environment | authorities, |  | locality | gets, OAR |  | developing such |
|  |  |  | NGOs, OAR, |  |  | stamp |  | studies |
|  |  |  | architecture |  |  | fee, NGO |  |  |
|  |  |  | and urbanism |  |  | funding |  |  |
|  |  |  | universities |  |  | lines |  |  |
|  | D1.13 | Integration of the studies into the Mas- | Local govt. | 2015 – 2020 | - | Own | Low | No. of Masterplans |
|  |  | terplans | authorities, |  |  | resources |  | integrating the |
|  |  |  | OAR |  |  |  |  | studies |
|  | D1.14 | Fiscal mechanisms to encourage the use | Local govern- | 2012 – 2013 | - | Own | Medium | No. of mechanisms |
|  |  | of the existing built assets rather than | ment authori- |  |  | resources |  | set up |
|  |  | new buildings | ties |  |  |  |  |  |
|  | D1.15 | Fiscal mechanisms (subsidies, tax breaks) | Local govern- | 2012 – 2013 | - | Own | High | No. of mechanisms |
|  |  | for terrace roof greening | ment authori- |  |  | resources |  | set up |
|  |  |  | ties |  |  |  |  |  |
|  | D1.16 | Revision of Law No. 24/ 2007 on regu- | MEF | 2012 | - | Own | High | Achieved/ not |
|  |  | lating and maaging green spaces within |  |  |  | resources |  | achieved |
|  |  | the localities to include the obligation to |  |  |  |  |  |  |
|  |  | green terrace roofs and rede"ne the con- |  |  |  |  |  |  |
|  |  | cept of green space, based on the natural |  |  |  |  |  |  |
|  |  | water cycle |  |  |  |  |  |  |
|  | D1.17 | Development of standards for green | MEF, universi- | 2012 – 2013 | 20,000 | OAR | Medium | Achieved/ not |
|  |  | spaces (species of plants recommended | ties, schools |  |  |  |  | achieved |
|  |  | for various uses – tree lines, green ter- | of architecture |  |  |  |  |  |
|  |  | races, parks, tra!c islands, etc.) | and horticul- |  |  |  |  |  |
|  |  |  | ture ASAS |  |  |  |  |  |

136

| TABLE CONTINUED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions |  |  |  |  |  |  | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  |  |  |  |  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | D1.18 | Adoption of the Romanian Architectural |  |  |  |  |  |  | MRDT, MEF, | 2012 | - | Own | Urgent | Achieved/ not |
|  |  | Policy and ensure consistency of the |  |  |  |  |  |  | MCNH, OAR |  |  | resources |  | achieved |
|  |  | land | use | development, |  |  | urbanism, |  |  |  |  |  |  |  |
|  |  | local | development |  | and |  | biodiversity |  |  |  |  |  |  |  |
|  |  | conservation policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | D2. | FOREST MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |
|  | D2.1 | Inclusion of relevant biodiversity conser- |  |  |  |  |  |  | MEF | 2012 | - | Own | Medium | Approved norms |
|  |  | vation aspects into the technical norms |  |  |  |  |  |  |  |  |  | resources |  |  |
|  |  | for developing forest management units |  |  |  |  |  |  |  |  |  |  |  |  |
|  | D2.2 | Institutional |  | capacity |  | building |  | for | MEF | 2012 – 2013 | - | Own | High | No. of positions |
|  |  | forestry enforcement |  |  |  |  |  |  |  |  |  | resources |  | created in the |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | ITRSV, No. of |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | equipment, No. of |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | trained sta! |
|  | D2.3 | Improvement of the legal and regulatory |  |  |  |  |  |  | MEF | 2012 | - | Own | Medium | Achieved/ not |
|  |  | framework and correlation with biodi- |  |  |  |  |  |  |  |  |  | resources |  | achieved |
|  |  | versity conservation regulations |  |  |  |  |  |  |  |  |  |  |  |  |
|  | D2.4 | Improvement of the legal framework for |  |  |  |  |  |  | MEF | 2012 – 2012 | - | Own | High | Achieved/ not |
|  |  | the management of private forests and |  |  |  |  |  |  |  |  |  | resources |  | achieved |
|  |  | compensation granting |  |  |  |  |  |  |  |  |  |  |  |  |
|  | D2.5 | Economic assessment of the protection |  |  |  |  |  |  | MEF | 2012 | 100,000 | State | High | Achieved/ not |
|  |  | functions of forests |  |  |  |  |  |  |  |  |  | Budget |  | achieved |
|  | D2.6 | Increased share of natural regeneration |  |  |  |  |  |  | MEF | 2012 – 2020 | - | Own | High | % of natural |
|  |  | by applying appropriate intensive treat- |  |  |  |  |  |  |  |  |  | resources |  | regeneration |
|  |  | ment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | D2.7 | Identi"cation of harvested and not re- |  |  |  |  |  |  | MEF | 2012 | - | Own | High | % of identi"ed land |
|  |  | generated forestry land |  |  |  |  |  |  |  |  |  | resources |  |  |

137

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | D2.8 | Enlargement of forest land and other | MEF | 2012 – 2020 | 500,000,000 | State | High | No. of ha extension |
|  |  | categories of forest vegetation, including |  |  |  | Budget, EF, |  |  |
|  |  | on degraded land outside the forestry |  |  |  | EFARD |  |  |
|  |  | stock |  |  |  |  |  |  |
|  | D3. | AGRICULTURE |  |  |  |  |  |  |
|  | D3.1 | Assessment of the positive versus nega- | MEF, MARD | 2012 – 2013 | 100,000 | State | High | No. of farming |
|  |  | tive impacts of agricultural policies and |  |  |  | Budget |  | practices assessed |
|  |  | practices in relation to biodiversity con- |  |  |  |  |  |  |
|  |  | servation |  |  |  |  |  |  |
|  | D3.2 | Update and adoption of the existing | MEF, MARD | 2012 – 2013 | - | Own | High | No. of updated |
|  |  | norms and guidelines to include agricul- |  |  |  | resources |  | norms and |
|  |  | tural best practice in the sustainable use |  |  |  |  |  | guidelines |
|  |  | of agri-biodiversity |  |  |  |  |  |  |
|  | D3.3 | Assessment of the impact of the current | MEF, MARD | 2012 – 2012 | - | Own | High | Achieved/ not |
|  |  | incentives/ subsidies/ state aid on biodi- |  |  |  | resources |  | achieved |
|  |  | versity conservation, in order to identify |  |  |  |  |  |  |
|  |  | and discard the perverse ones |  |  |  |  |  |  |
|  | D3.4 | Development of further incentives and | MEF, MARD | 2012 – 2013 | - | Own | High | No. of !scal incen- |
|  |  | appropriate !scal mechanisms for biodi- |  |  |  | resources |  | tives, and mecha- |
|  |  | versity conservation |  |  |  |  |  | nisms developed |
|  | D3.5 | Assessment of the capacity of various | MEF, MARD | 2012 – 2014 | 10,000/ | State | Medium | No. of production |
|  |  | agricultural production systems for agri- |  |  | study | Budget, EF, |  | systems assessed |
|  |  | biodiversity conservation and sustainable |  |  |  | external |  |  |
|  |  | use of resources, that foster economic ef- |  |  |  | funds |  |  |
|  |  | !ciency |  |  |  |  |  |  |

138

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting indicators |
|  |  |  | institutions |  | (EUR) | sources |  |  |
|  | D3.6 | Investigation of agri-biodiversity uses in | MEF, MARD | 2012 – 2013 | 300,000 | State | Low | Achieved/ not |
|  |  | the sustainable development of agricul- |  |  |  | Budget, EF, |  | achieved |
|  |  | tural systems that help improve living |  |  |  | external |  |  |
|  |  | standards, also ensuing improvement of |  |  |  | funds |  |  |
|  |  | the state of biodiversity, by conserving |  |  |  |  |  |  |
|  |  | the most useful and vulnerable species |  |  |  |  |  |  |
|  | D3.7 | Evaluation and characterisation of local | MARD | 2012 – 2013 | 300,000 | State | Medium | No. of local strands, |
|  |  | strands, hybrids and breeds to identify |  |  |  | Budget, EF, |  | hybrids and breeds |
|  |  | those with high potential to adapt to cli- |  |  |  | external |  | with high potential |
|  |  | mate change |  |  |  | funds |  | to adapt to climate |
|  |  |  |  |  |  |  |  | change |
|  | D3.8 | Expansion of agri-forest-pastoral sys- | MEF, MARD, | 2012 – 2020 | 10,000/ ha | State | High | Area extension of |
|  |  | tems to areas of high risk of aridisation | MRDT |  |  | Budget, EF, |  | agri-forest-pastoral |
|  |  |  |  |  |  | EFARD. |  | systems |
|  |  |  |  |  |  | LIFE+ |  |  |
|  | D3.9 | Development of national level studies | MARD | 2012 – 2012 | - | Own | High | Achieved/ not |
|  |  | of the current fragmentation of farming |  |  |  | resources |  | achieved |
|  |  | plots, the causes and consequences of |  |  |  |  |  |  |
|  |  | such fragmentation |  |  |  |  |  |  |
|  | D3.10 | Development of national level studies of | MARD | 2012 – 2013 | - | Own | High | Achieved/ not |
|  |  | land conversion, types of land uses re- |  |  |  | resources |  | achieved |
|  |  | placed, type of land replacing traditional |  |  |  |  |  |  |
|  |  | uses |  |  |  |  |  |  |
|  | D3.11 | Assessment studies on bio-diesel, etha- | MEF | 2012 – 2013 | - | Own | High | Achieved/ not |
|  |  | nol and biomass crop impacts on biodi- |  |  |  | resources |  | achieved |
|  |  | versity |  |  |  |  |  |  |
|  | D3.12 | Inventory of native breeds and adoption | MARD | 2012 – 2012 | - | Own | High | Achieved/ not |
|  |  | thereof under a regulation |  |  |  | resources |  | achieved |

139

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | D3.13 | Creation of mechanisms to promote the | MARD | 2012 – 2013 |  | Own | High | Achieved/ not |
|  |  | type approval and use of native breeds |  |  |  | resources |  | achieved |
|  |  | and strains |  |  |  |  |  |  |
|  | D3.14 | Development of a national strategy for | MEF, MARD | 2012 – 2012 | 200,000 | Own | High | Achieved/ not |
|  |  | the testing, cultivation and use of geneti- |  |  |  | resources |  | achieved |
|  |  | cally modi"ed organisms |  |  |  |  |  |  |
|  | D4. | HARVESTING OF WILD SPECIES OF ECONOMIC VALUE |  |  |  |  |  |  |
|  | D4.1 | Set up and approval of technical norms | MEF, MARD | 2012 – 2012 | 30,000 | State | High | No. of technical |
|  |  | and standard methodologies for the as- |  |  |  | Budget |  | norms and stan- |
|  |  | sessment of wildlife species of economic |  |  |  |  |  | dard methodolo- |
|  |  | interest in their natural environment |  |  |  |  |  | gies approved |
|  | D4.2 | Set up and approval of techniques/ | MEF, MARD | 2012 – 2012 | 30,000 | State | High | No. of species with |
|  |  | methods of harvesting/ capturing wildlife |  |  |  | Budget |  | harvesting/ captur- |
|  |  | species of economic interest |  |  |  |  |  | ing techniques/ |
|  |  |  |  |  |  |  |  | methods approved |
|  | D4.3 | Annual assessment of the conservation | MEF, MARD | 2012 – 2020 | 500,000/ | State | Medium | No. of species as- |
|  |  | status of species with economic value |  |  | year | Budget |  | sessed/ year |
|  | D4.4 | Updated Fishing Management Program | MARD, MEF | 2013 – 2015 | - | Own | Medium | Achieved/ not |
|  |  |  |  |  |  | resources |  | achieved |
|  | D4.5 | Improved enforcement of the regulations | MEF | 2012 – 2020 | - | Own | High | No. of inspections |
|  |  | on assessing the numbers of individuals |  |  |  | resources |  |  |
|  |  | of species of economic interest |  |  |  |  |  |  |
|  | D4.6 | Strengthening enforcement in harve- | MEF | 2012 – 2020 | - | Own | High | No. of inspections |
|  |  | sting/ capturing and trade in species of |  |  |  | resources |  |  |
|  |  | economic value |  |  |  |  |  |  |

140

| TABLE CONTINUED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Period |  |
|  |  | Actions | Responsible |  |  |
|  |  |  | institutions |  |  |
|  | D5. |  |  |  |  |
|  |  | TOURISM |  |  |  |
|  | D5.1 |  |  | 2012 – 2013 |  |
|  |  | Development and adoption of the Good | MEF, MRDT |  |  |
|  |  | Practice Guidance for sustainable tourism |  |  |  |
|  |  | development |  |  |  |
|  | D5.2 | Integration of a dedicated chapter on the | MRDT | 2012 |  |
|  |  | conservation and sustainable capitalisa- |  |  |  |
|  |  | tion of landscapes into the Tourism Mas- |  |  |  |
|  |  | terplan 2007-2026 and into the tourism |  |  |  |
|  |  | development policies |  |  |  |
|  | D5.3 | Development of !nancial mechanisms for | MEF, MRDT | 2012 – 2013 |  |
|  |  | the contribution of the tourism sector to |  |  |  |
|  |  | biodiversity and landscape conservation |  |  |  |
|  | D5.4 | Implementation of eco-labelling systems | MEF, MRDT | 2012 – 2015 |  |
|  |  | for tourist accommodation services |  |  |  |
|  | D5.5 | Set up and adoption of !scal facilities for | MEF, MRDT | 2012 – 2013 |  |
|  |  | tourism businesses implementing eco- |  |  |  |
|  |  | labelling systems |  |  |  |
|  | D6. |  |  |  |  |
|  |  | TRANSPORT, ENERGY AND USE OF NON-RENEWABLE RESOURCES |  |  |  |
|  | D6.1 |  |  | 2012 – 2013 |  |
|  |  | Development of !nancial mechanisms | MEF, MCMA |  |  |
|  |  | for the contribution of the energy and |  |  |  |
|  |  | non-renewable resource (other than fos- |  |  |  |
|  |  | sil fuels) sectors to biodiversity and land- |  |  |  |
|  |  | scape conservation |  |  |  |

| Budget | Funding | Priority | Reporting |  |
| --- | --- | --- | --- | --- |
| (EUR) | sources |  | indicators |  |
|  |  |  | Achieved/ not |  |
| 200,000 | State | Medium |  |  |
|  | Budget, EF, |  | achieved |  |
|  | external |  |  |  |
|  | funds |  |  |  |
| - | Own | Low | Achieved/ not |  |
|  | resources |  | achieved |  |

| - | Own | High | No. of !nancial |
| --- | --- | --- | --- |
|  | resources |  | mechanisms set up |
| - | Own | Medium | No. of tourist |
|  | resources |  | facilities and agents |
|  |  |  | adopting the eco- |
|  |  |  | labelling schemes |
| - | Own | Medium | No. of mechanisms |
|  | resources |  | adopted |

| - | Own | High | No. of !nancial |
| --- | --- | --- | --- |
|  | resources |  | mechanisms set up |

141

| TABLE CONTINUED |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |  |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |  |
|  | D6.2 | Inclusion of biodiversity conservation | MEF | 2012 – 2012 | - | Own | High | Achieved/ not |  |
|  |  | considerations into the technical norms |  |  |  | resources |  | achieved |  |
|  |  | for calculating the biological base!ows |  |  |  |  |  |  |  |
|  | D6.3 | National study to identify the areas of | MEF | 2012 – 2013 | 50,000 | State | Urgent | Achieved/ not |  |
|  |  | windfarm development bans, based on |  |  |  | Budget |  | achieved |  |
|  |  | major impacts on biodiversity |  |  |  |  |  |  |  |
|  | D6.4 | National study to identify the areas of | MEF | 2012 – 2013 | 50,000 | State | High | Achieved/ not |  |
|  |  | hydro-power development bans, based |  |  |  | Budget |  | achieved |  |
|  |  | on major impacts on biodiversity |  |  |  |  |  |  |  |
|  | D6.5 | Assessment of how the current road | MEF, MTI | 2012 – 2016 | 300,000 | Environ- | Low | % of transport in- |  |
|  |  | network fragments the natural habitats |  |  |  | mental |  | frastructure length |  |
|  |  | of wildlife species of conservation value |  |  |  | Fund |  | assessed |  |
|  |  | and proposed solution to reduce/ Control |  |  |  |  |  |  |  |
|  |  | fragmentation (ecoducts, fauna bridges, |  |  |  |  |  |  |  |
|  |  | etc.) |  |  |  |  |  |  |  |
|  | D6.6 | Development and adoption of regula- | MEF | 2012 | - | Own | Urgent | Achieved/ not |  |
|  |  | tion on SUV (cars, motorcycles, ATVs), |  |  |  | resources |  | achieved |  |
|  |  | aquatic (scooters, powerboats), snow |  |  |  |  |  |  |  |
|  |  | vehicle (snow mobile) tra"c |  |  |  |  |  |  |  |
|  | D6.7 | Adoption of speci!c regulations to con- | MEF, MTI | 2012 | - | Own | High | Achieved/ not |  |
|  |  | sider biodiversity conservation under |  |  |  | resources |  | achieved |  |
|  |  | article 55 and 56 o$he Air Law |  |  |  |  |  |  |  |
|  | E. | EX SITU CONSERVATION |  |  |  |  |  |  |  |
|  | E.1 | Assessment of the operations of gene | MEF, MARD, | 2012 – 2013 | - | Own | Low | Achieved/ not |  |
|  |  | banks, captive wild animal keeping facil- | MERYS |  |  | resources, |  | achieved |  |
|  |  | ities and collections of wild plants (seed |  |  |  |  |  |  |  |
|  |  |  |  |  |  | State |  |  |  |
|  |  | banks, botanical gardens, tree stands, |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Budget |  |  |  |
|  |  | tree parks, etc.) |  |  |  |  |  |  |  |

142

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | E.2 | Inventory and assessment of the | MARD | 2012 – 2014 | 500,000 | State | Medium | No. of species, hy- |
|  |  | conservation status of local native |  |  |  | Budget |  | brids and breeds |
|  |  | species, strands, hybrids and breeds |  |  |  |  |  | inventoried and |
|  |  | used in agriculture and industry |  |  |  |  |  | assessed |
|  | E.3 | Set up and adoption of new zoo standards, | MEF, NGOs | 2012 – 2013 | - | Own | High | Achieved/ not |
|  |  | in consideration of their role in wildlife |  |  |  | resources |  | achieved |
|  |  | species conservation and education |  |  |  |  |  |  |
|  | F. | CONTROL OF INVASIVE ALIEN SPECIES |  |  |  |  |  |  |
|  | F.1 | National list of invasive species | MEF, MERYS, | 2012 – 2013 | 300,000 | State | High | Achieved/ not |
|  |  |  | RA |  |  | Budget, EF |  | achieved |
|  | F.2 | Development and maintenance of a regis- | MEF | 2012 | 100,000 | Own | Medium | No. of species |
|  |  | ter and database of alien species |  |  |  | resources |  | entered |
|  | F.3 | Development of a Common Sectoral Plan | MEF, MARD | 2012 – 2020 | 100,000 | State | High | Achieved/ not |
|  |  | for the assessment based on rigorous sci- |  |  |  | Budget, |  | achieved |
|  |  | enti!c knowledge, of the behaviour of |  |  |  | external |  |  |
|  |  | alien species in the Romanian soil-cli- |  |  |  | funds |  |  |
|  |  | mate conditions, in order to establish a |  |  |  |  |  |  |
|  |  | framework (guidelines) for the develop- |  |  |  |  |  |  |
|  |  | ment of procedures |  |  |  |  |  |  |
|  | F.4 | Development and adoption of technical | MEF, NEG, AV | 2012 | - | Own | High | Achieved/ not |
|  |  | norms on the introduction and control of |  |  |  | resources |  | achieved |
|  |  | alien species from neighbouring and/ or |  |  |  |  |  |  |
|  |  | exotic areas |  |  |  |  |  |  |
|  | F.5 | Rati!cation of the Convention on Ballast | MEF, MTI, | 2012 | - | Own | High | Achieved/ not |
|  |  | Water Management (BWM) and devel- | MAE |  |  | resources |  | achieved |
|  |  | opment of further implementation mea- |  |  |  |  |  |  |
|  |  | sures |  |  |  |  |  |  |

143

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | F.6 | Development of administrative mecha- | MEF, MECBE | 2012 – 2014 | - | Own | Medium | Achieved/ not |
|  |  | nisms for the monitoring of alien species |  |  |  | resources |  | achieved |
|  |  | introduced for economic purposes |  |  |  |  |  |  |
|  | F.7 | Setting up of a reporting mechanism and/ | MEF | 2012 – 2012 | - | Own | Medium | No. of species with |
|  |  | or surveillance line for the most endan- |  |  |  | resources |  | mechanisms set up |
|  |  | gered taxons or species used as pets, to |  |  |  |  |  |  |
|  |  | !ag the accidental or deliberate introduc- |  |  |  |  |  |  |
|  |  | tion into the wild |  |  |  |  |  |  |
|  | F.8 | Mandatory monitoring of bilge waters | MEF | 2012 – 2012 | - | Own | Medium | Achieved/ not |
|  |  | and fouling on boats discharging bilge |  |  |  | resources |  | achieved |
|  |  | water or careening in harbours, and of |  |  |  |  |  |  |
|  |  | sediments on the bottom of bilge tanks |  |  |  |  |  |  |
|  |  | where resistance forms may develop |  |  |  |  |  |  |
|  | F.9 | Publicly accessible databases with infor- | MEF, MERYS, | 2012 – 2013 | - | Own | Medium | Achieved/ not |
|  |  | mation on the risks associated to inten- | RA |  |  | resources, |  | achieved |
|  |  | tionally species introduced for various |  |  |  | State |  |  |
|  |  | purposes |  |  |  | Budget |  |  |
|  | F.10 | Strict monitoring of alien species intro- | MEF, MARD | 2012 – 2020 | Not | Aquatic | Medium | No. of species and |
|  |  | duced for aquaculture that may spread |  |  | estimated | resource |  | locations moni- |
|  |  | and naturalise into aquatic ecosystems |  |  |  | adminis- |  | tored |
|  |  |  |  |  |  | trators |  |  |
|  | F.11 | Development of management plans for | MEF | 2012 – 2013 | 500,000 | Own | High | No. of developed |
|  |  | maximum risk pathways |  |  |  | resources, |  | plans |
|  |  |  |  |  |  | external |  |  |
|  |  |  |  |  |  | funds |  |  |
|  | F.12 | Implementation of management plans for | MEF | 2013 – 2020 | Not | Own | High | No. of plans imple- |
|  |  | maximum risk pathways |  |  | estimated | resources |  | mented |

144

| TABLE CONTINUED |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  | institutions |  | (EUR) | sources |  | indicators |
| F.13 | Assessment of the risks of invasive spe- | MEF | 2012 – 2013 | 60,000 | Own | High | Achieved/ not |
|  | cies over native species in order to iden- |  |  |  | resources, |  | achieved |
|  | tify and prioritise management options |  |  |  | external |  |  |
|  | thereof |  |  |  | funds |  |  |
| F.14 | Development of monitoring indicators of | MEF | 2012 – 2013 | 20,000 | Own | Medium | No. of indicators |
|  | invasive species impacts |  |  |  | resources, |  | developed |
|  |  |  |  |  | external |  |  |
|  |  |  |  |  | funds |  |  |
| F.15 | Development of methods/ methodolo- | MEF | 2012 – 2013 | 100,000 | Own | Medium | No. of developed |
|  | gies to limit, control and eradicate alien |  |  |  | resources, |  | methodologies |
|  | invasive species |  |  |  | external |  |  |
|  |  |  |  |  | funds |  |  |

G.	ACCESS TO GENETIC RESOURCES AND FAIR DISTRIBUTION OF BENEFITS IN THE USE OF SUCH RESOURCES (ABS)

| G.1 | Preparation of a legal and institutional | MEF, MARD, | 2012 – 2012 | - | Own | High | Achieved/ not |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | framework for the implementation of the | MERYS |  |  | resources, |  | achieved |
|  | Protocol on the ABS regime |  |  |  | State |  |  |
|  |  |  |  |  | Budget |  |  |
| G.2 | Adopting and implementing the Bonn | MEF, MARD, | 2012 | - | Own | Low | Achieved/ not |
|  | guidelines | MERYS |  |  | resources, |  | achieved |
|  |  |  |  |  | State |  |  |
|  |  |  |  |  | Budget |  |  |
| G.3 | Development of a legal framework and | MEF, MARD, | 2012 – 2015 | - | Own | High | Achieved/ not |
|  | the necessary !nancial mechanisms for | MECBE/ |  |  | resources |  | achieved |
|  | the recognition of intellectual property | OSIM |  |  |  |  |  |
|  | rights on access to genetic resources |  |  |  |  |  |  |
|  | and traditional ways of using genetic |  |  |  |  |  |  |
|  | resources |  |  |  |  |  |  |

145

| TABLE CONTINUED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions |  |  |  |  |  | Responsible | Period | Budget (EUR) | Funding |  | Priority | Reporting |
|  |  |  |  |  |  |  |  | institutions |  |  | sources |  |  | indicators |
|  | G.4 | Establishing monitoring indicators |  |  |  |  |  | MEF | 2012-2013 | - | Own |  | Medium | Achieved/ not |
|  |  | for ABS implementation |  |  |  |  |  |  |  |  | resources |  |  | achieved |
|  | H. | SUPPORT AND PROMOTION OF TRADITIONAL KNOWLEDGE, INNOVATION AND PRACTICES |  |  |  |  |  |  |  |  |  |  |  |  |
|  | H.1 | Adopting the Cologne guidelines |  |  |  |  |  | MEF, MARD, | 2012 | - | Own |  | Medium | Achieved/ not |
|  |  |  |  |  |  |  |  | MERYS |  |  | resources, |  |  | achieved |
|  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  |  |
|  | H.2 | Inventory | of | traditional |  | natural |  | MEF, MARD, | 2012 – 2012 | Not estimated | Own |  | Medium | Achieved/ not |
|  |  | resource | use |  | practices |  | and | MCNH, |  |  | resources, |  |  | achieved |
|  |  | assessment of their impact on |  |  |  |  |  | MERYS |  |  | State Budget |  |  |  |
|  |  | biodiversity conservation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | H.3 | Development of regulations on in- |  |  |  |  |  | MEF, MARD, | 2012 – 2015 | - | Own |  | Medium | Achieved/ not |
|  |  | tellectual property rights for tradi- |  |  |  |  |  | OSIM |  |  | resources |  |  | achieved |
|  |  | tional knowledge and methods of |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | genetic resources use |  |  |  |  |  |  |  |  |  |  |  |  |
|  | H.4 | Setting up mechanisms for the |  |  |  |  |  | MEF, MARD | 2013 – 2015 | - | Own |  | Medium | No. of !nancial |
|  |  | promotion of the use of traditional |  |  |  |  |  |  |  |  | resources |  |  | mechanisms |
|  |  | practices for the sustainable use of |  |  |  |  |  |  |  |  |  |  |  | set up |
|  |  | natural resources |  |  |  |  |  |  |  |  |  |  |  |  |
|  | I. | DEVELOPMENT OF SCIENTIFIC RESEARCH AND PROMOTION OF TECHNOLOGY TRANSFER |  |  |  |  |  |  |  |  |  |  |  |  |
|  | I.1 | Development |  | of | the | National |  | MERYS | 2012 – 2013 | - | Own re- |  | High | Achieved/ not |
|  |  | Taxonomy Program |  |  |  |  |  |  |  |  | sources |  |  | achieved |
|  | I.2 | Creating | incentive mechanisms |  |  |  |  | MERYS, | 2012 – 2014 | - | Own re- |  | Urgent | No. of |
|  |  | for researchers |  |  | specialising |  | in | universi- |  |  | sources |  |  | institutions with |
|  |  | taxonomy |  |  |  |  |  | ties research |  |  |  |  |  | mechanisms |
|  |  |  |  |  |  |  |  | institutes, |  |  |  |  |  | established |
|  |  |  |  |  |  |  |  | museums |  |  |  |  |  |  |

146

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | I.3 | Development of species and natural habi- | universities | 2012 – 2020 | 300,000/ | State | High | No. of |
|  |  | tat determination guidelines, !eld guide- | research insti- |  | year | Budget, |  | determinators/ |
|  |  | books and atlases for Romania | tutes, muse- |  |  | earmarked |  | guidebooks/ atlases |
|  |  |  | ums, profes- |  |  | research |  | developed |
|  |  |  | sional NGOs |  |  | funds |  |  |
|  | I.4 | Integration of dedicated programs into | MEF, MERYS | 2012 – 2012 | - | Own | High | No. of programs |
|  |  | the existing funding lines for biodiversity |  |  |  | resources |  | set up |
|  |  | conservation, with the view of supporting |  |  |  |  |  |  |
|  |  | applied research in establishing the |  |  |  |  |  |  |
|  |  | methods and techniques for the |  |  |  |  |  |  |
|  |  | mitigation of climate change impacts on |  |  |  |  |  |  |
|  |  | genetic resources |  |  |  |  |  |  |
|  | I.5 | Integration of the ecosystem approach | MEF, MERYS | 2012 – 2013 | - | Own | High | Achieved/ not |
|  |  | into the National Strategy for Research, |  |  |  | resources |  | achieved |
|  |  | Development and Innovation |  |  |  |  |  |  |
|  | I.6 | Development of a database to integrate | MERYS | 2012 – 2014 | - | Own | Low | Achieved/ not |
|  |  | the results of studies and research funded |  |  |  | resources, |  | achieved |
|  |  | from public sources in biodiversity con- |  |  |  | State |  |  |
|  |  | servation |  |  |  | Budget |  |  |
|  | I.7 | Needs assessment for the transfer of tech- | MEF, MERYS, | 2012 – 2013 | - | Own | Medium | No. of necessary |
|  |  | nology in the conservation and sustain- | MARD, MTI, |  |  | resources, |  | technologies |
|  |  | able use of biological diversity | MECBE |  |  | State |  |  |
|  |  |  |  |  |  | Budget |  |  |
|  | I.8 | Setting up of mechanisms to facilitate the | MEF, MERYS, | 2013 – 2015 | - | Own | Medium | No. of partnerships |
|  |  | transfer of new technologies in the con- | MARD, MTI, |  |  | resources, |  | set up |
|  |  | servation and sustainable use of biologi- | MECBE |  |  | bugetul de |  |  |
|  |  | cal diversity |  |  |  | stat |  |  |

TABLE CONTINUED

147

|  | Actions | Responsible | Period |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | institutions |  |  |  |
| I.9 | Setting up of mechanisms to facilitate the | MEF, MERYS, | 2013 – 2015 |  |  |
|  | patenting of new technologies in the con- | MARD, MTI, |  |  |  |
|  | servation and sustainable use of biologi- | MECBE |  |  |  |
|  | cal diversity |  |  |  |  |
| I.10 | Setting up mechanisms to facilitate access | MEF, MECBE, | 2012 – 2013 |  |  |
|  | to community funds for eco-innovation | MRDT, |  |  |  |
|  | in support of the ETAP roadmap | MERYS, |  |  |  |
|  |  | ANCS, AN- |  |  |  |
|  |  | RMAP, EF, |  |  |  |
|  |  | INCDPM, |  |  |  |
|  |  | ECOIND, |  |  |  |
|  |  | CCIR |  |  |  |
| I.11 | Implementing molecular technologies in | Universities, | 2012 – 2020 |  |  |
|  | routine analyses to characterise species of | research |  |  |  |
|  | conservation concern, invasive species, | Institutes |  |  |  |
|  | etc. |  |  |  |  |
| J. |  |  |  |  |  |
|  | PUBLIC COMMUNICATION, EDUCATION AND AWARENESS RAISING |  |  |  |  |
| J.1 |  |  |  |  |  |
|  | Establishing an internal communication | MEF | 2012 – 2012 |  |  |
|  | strategy among environmental authori- |  |  |  |  |
|  | ties |  |  |  |  |
| J.2 | Implementation of the CEPA Action | MEF | 2012 – 2015 |  |  |
|  | Plan |  |  |  |  |

| Budget | Funding | Priority | Reporting |
| --- | --- | --- | --- |
| (EUR) | sources |  | indicators |
| - | Own | Medium | No. of patents |
|  | resources, |  |  |
|  | State |  |  |
|  | Budget |  |  |
| - | Own | Medium | Amounts accessed |
|  | resources, |  |  |
|  | State |  |  |
|  | Budget |  |  |

| Not | State | High | Nucleotide |  |
| --- | --- | --- | --- | --- |
| estimated | Budget, |  | sequences (bar |  |
|  | earmarked |  | codes) publications |  |
|  | research |  |  |  |
|  | funds |  |  |  |
|  |  |  | Achieved/ not |  |
| 50,000 | State | High |  |  |
|  | Budget |  | achieved |  |
| Not | State | High | Achieved/ not |  |
| estimated | Budget, EF, |  | achieved |  |
|  | SOP Env., |  |  |  |
|  | external |  |  |  |
|  | funds |  |  |  |

148

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | J.3 | Designation of focal points for the mana- | MEF, MARD, | 2012 – 2012 | - | Own | High | No. of authorities |
|  |  | gement of information on biodiversity | MERYS, |  |  | resources |  | with designated |
|  |  | conservation for all the stakeholders | MRDT, MAI, |  |  |  |  | focal points |
|  |  |  | MEA, MND, |  |  |  |  |  |
|  |  |  | MCNH, |  |  |  |  |  |
|  |  |  | MRSE, |  |  |  |  |  |
|  |  |  | MECBE, MPF, |  |  |  |  |  |
|  |  |  | MTI, MMFPS |  |  |  |  |  |
|  |  |  | and subordi- |  |  |  |  |  |
|  |  |  | nated units |  |  |  |  |  |
|  | J.4 | Establishing a functional communication | MEF, MARD, | 2012 – 2015 | - | Own | High | No. of consulta- |
|  |  | network among those in charge of biodi- | MERYS, |  |  | resources |  | tions, No. of deci- |
|  |  | versity conservation in the central and lo- | MRDT, MAI, |  |  |  |  | sions made base |
|  |  | cal environmental public authorities | MEA MND, |  |  |  |  | on information |
|  |  |  | MCNH, |  |  |  |  | sharing |
|  |  |  | MRSE, |  |  |  |  |  |
|  |  |  | MECBE, MPF, |  |  |  |  |  |
|  |  |  | MTI, MMFPS |  |  |  |  |  |
|  |  |  | and subordi- |  |  |  |  |  |
|  |  |  | nated units, |  |  |  |  |  |
|  |  |  | local govt. |  |  |  |  |  |
|  |  |  | authorities |  |  |  |  |  |
|  | J.5 | Assessment of local community involve- | MEF, ad- | 2012 – 2020 | - | Own | Medium | No. of participants |
|  |  | ment in major decision making for natu- | ministrators/ |  |  | resources |  | in public hearings |
|  |  | ral protected area management | custodians |  |  |  |  | on plans/ projects |
|  |  |  |  |  |  |  |  | in natural protect- |
|  |  |  |  |  |  |  |  | ed areas |

| TABLE CONTINUED |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actions | Responsible | Period | Budget | Funding | Priority | Reporting |
|  |  |  | institutions |  | (EUR) | sources |  | indicators |
|  | J.6 | Setting up an incentive mechanism for | MEF, adminis- | 2012 – 2012 | - | Own | Medium | No. of initiatives, |
|  |  | voluntary involvement in support of | trators/ custo- |  |  | resources |  | No. of volunteers |
|  |  | biodiversity conservation activities | dians, NGOs, |  |  |  |  |  |
|  |  |  | mass media |  |  |  |  |  |
|  | J.7 | Development of school curricula (pri- | MERYS | 2012 – 2013 | - | Own | Low | No. of curricula |
|  |  | mary, middle and high school level) for |  |  |  | resources |  | containing |
|  |  | mandatory introduction of basic bio- |  |  |  |  |  | subjects related |
|  |  | logical diversity concepts and the im- |  |  |  |  |  | to biodiversity |
|  |  | portance of conservation |  |  |  |  |  | conservation |
|  | J.8 | Development of school, undergraduate, | MERYS, | 2012 – 2013 | - | Own | Medium | No. of training |
|  |  | graduate and lifelong education train- | ARACIS |  |  | resources |  | curricula |
|  |  | ing programs in the area of natural capi- |  |  |  |  |  | developed |
|  |  | tal conservation |  |  |  |  |  |  |
|  | J.9 | Maintenance and ongoing updating of | MEF | 2012 – 2020 | - | Own | High | Achieved/ not |
|  |  | the CBD CHM |  |  |  | resources |  | achieved |

149

PDF to Word